## 14-1 JPA Printout
County | Municipality | Date Initial Letter Sent | Initial Delivery Confirmation | No Response Follow-up Letter Sent | No Response Follow-up Delivery Confirmation | Response Received | Notification for Changes | Notification for Changes Delivery Confirmation | Stormwater Plan Consistent | Floodplain Consistent
Blair | Juniata | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2/17/16 Sent twp Stormwater regulations | 2016-11-02 | 2016-11-03 | Y | Y
| Allegheny | 2015-11-10 | 2015-11-12 | N/A | N/A | 2015-11-20 | N/A | N/A | Y | Y
| Blair | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2016-02-16 | 2016-11-02 | 2016-11-03 | Y | Y
| Frankstown | 2015-11-10 | 2015-11-12 | N/A | N/A | 2015-11-20 | 2016-11-02 | 2016-11-03 | Y | Y
| Woodbury | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-12-14 | 2016-11-02 | 2016-11-03 | NO PLAN | Y
Huntingdon | Penn | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2016-02-16 | 2016-11-02 | 2016-11-03 | Y | Y
| Union | 2015-11-10 | 2015-11-12 | N/A | N/A | 2015-12-17 | 2016-11-02 | 2016-11-03 | Y | NO PLAN
| Shirley | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-12-07 | 2016-11-02 | 2016-11-03 | Y | Y
| Tell | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-11-16 | 2016-11-02 | 2016-11-03 | NO PLAN | Y
Juniata | Lack | 2015-11-10 | 2015-11-11 | N/A | N/A | None required - No Act 167 Plan | 2016-11-02 | 2016-11-03 | NO PLAN | NR
Perry | Toboyne | 2015-11-10 | 2015-11-11 | N/A | N/A | None required - No Act 167 Plan | 2016-11-02 | 2016-11-03 | NO PLAN | NR
| Jackson | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-11-24 | 2016-11-02 | 2016-11-03 | Y | Y
Cumberland | Lower Mifflin | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-11-24 | 2016-11-02 | 2016-11-03 | NO PLAN | Y
| Upper Frankford | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2/22/16 More information requested | 2016-11-02 | 2016-11-03 | Y** | Y
| Lower Frankford | 2015-11-10 | 2015-11-11 | N/A | N/A | 2016-01-20 | 2016-11-02 | 2016-11-04 | Y | Y
| North Middleton | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2016-01-21 | 2016-11-02 | 2016-11-03 | Y | Y
| Middlesex | 2015-11-10 | 2015-11-12 | N/A | N/A | 2015-11-30 | 2016-11-02 | 2016-11-03 | Y | Y
| Silver Spring | 2015-11-10 | 2015-11-11 | N/A | N/A | 2016-03-08 | 2016-11-02 | 2016-11-03 | Y | Y
| Monroe | 2015-11-10 | 2015-11-12 | N/A | N/A | 2016-02-12 | 2016-11-02 | 2016-11-03 | Y | Y
| Upper Allen | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2/12/16 More time requested | 2016-11-02 | 2016-11-03 | Y | Y
| Lower Allen | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2/18/16 More information requsted | 2016-11-02 | 2016-11-03 | Y | Y
York | Fairview | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | NR | N/A | N/A | Y** | NR
Dauphin | Lower Swatara | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-12-07 | 2016-11-02 | 2016-11-03 | Y | Y
| Highspire | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2016-02-11 | 2016-11-02 | 2016-01-03 | Y | Y
| Middletown | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 3/1/2016 More information requested | N/A | N/A | Y | N/A
| Londonderry | 2015-11-10 | 2015-11-12 | N/A | N/A | 2015-12-17 | N/A | N/A | Y | Y
| Derry | 2015-11-10 | 2015-11-11 | N/A | N/A | 2016-11-21 | N/A | N/A | Y | Y
| Conewago | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-12-14 | N/A | N/A | Y | Y
Lebanon | South Londonderry | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-11-30 | 2016-11-02 | 2016-11-03 | TBD* | Y
| South Annville | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2016-03-25 | 2016-11-02 | 2016-11-03 | N/A** | Y**
| West Cornwall | 2015-11-10 | 2015-11-11 | N/A | N/A | 2016-11-16 | 2016-11-02 | 2016-11-09 | N/A** | Y**
| Cornwall | 2015-11-10 | 2015-11-11 | N/A | N/A | 2015-11-24 | 2016-11-02 | 2016-11-03 | Y | Y
| South Lebanon | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2016-03-25 | 2016-11-02 | 2016-11-03 | Y** | Y**
| Heidelberg | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2016-08-11 | 2016-11-02 | 2016-11-03 | Y** | Y
Lancaster | Clay | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | NR | 2016-11-02 | 2016-11-03 | NR | NR
| West Cocalico | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2015-12-28 | 2016-11-02 | 2016-11-03 | Y | Y
Berks | South Heidelberg | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2/11/16 More information requested | 2016-11-02 | 2016-11-03 | Y | Y
| Spring | 2015-11-10 | 2015-11-12 | N/A | N/A | 2015-11-17 | 2016-11-02 | 2016-11-03 | Y | Y
| Cumru | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | NR | 2016-11-02 | 2016-11-03 | NR | N/A
| Brecknock | 2015-11-10 | 2015-11-11 | 2016-02-08 | 2016-02-09 | 2016-02-26 | 2016-11-04 | 2016-11-07 | Y | Y
| Robeson | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2016-09-09 | 2016-11-02 | 2016-11-03 | Y | Y
| New Morgan | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 2016-06-15 | 2016-11-02 | 2016-11-03 | Y | Y
| Caernarvon | 2015-11-10 | 2015-11-12 | 2016-02-08 | 2016-02-09 | 12/11/15 More information requested | 2016-11-04 | 2016-11-07 | TBD* | TBD*

## 14-2 JPA Printout
County | Municipality | Stormwater Plan Consistent | Floodplain Consistent | Follow-Up Summary
Blair | Juniata | Y | Y
| Allegheny | Y | Y
| Blair | Y | Y
| Frankstown | Y | Y
| Woodbury | NO PLAN | Y
Huntingdon | Penn | Y | Y
| Union | Y | NO PLAN
| Shirley | Y | Y
| Tell | NO PLAN | Y
Juniata | Lack | NO PLAN | NR
Perry | Toboyne | NO PLAN | NR
| Jackson | Y | Y
Cumberland | Lower Mifflin | NO PLAN | Y
| Upper Frankford | Y** | Y
| Lower Frankford | Y | Y
| North Middleton | Y | Y
| Middlesex | Y | Y
| Silver Spring | Y | Y
| Monroe | Y | Y
| Upper Allen | Y | Y
| Lower Allen | Y | Y
York | Fairview | Y** | NR
Dauphin | Lower Swatara | Y | Y
| Highspire | Y | Y
| Middletown | Y | N/A
| Londonderry | Y | Y
| Derry | Y | Y
| Conewago | Y | Y
Lebanon | South Londonderry | TBD* | Y | South Londonderry Township requested erosion and sediment control plans which SPLP submitted to the Township in June 2016. The Township reviewed the plans and submitted comments on 9/15/16. S. Londonderry is asking for CCD & DEP approvals, a riparian corridor easement, cost estimates for E&S improvements & performance security prior to construction occurring. SPLP sent a response letter to the Township on 11/4/16.
| South Annville | N/A** | Y**
| West Cornwall | N/A** | Y**
| Cornwall | Y | Y
| South Lebanon | Y** | Y**
| Heidelberg | Y** | Y
Lancaster | Clay | NR | NR
| West Cocalico | Y | Y
Berks | South Heidelberg | Y | Y
| Spring | Y | Y
| Cumru | NR | N/A
| Brecknock | Y | Y
| Robeson | Y | Y
| New Morgan | Y | Y
| Caernarvon | TBD* | TBD* | Caernarvon Township requested erosion and sediment control plans, which SPLP submitted to the Township in June 2016. Since this submittal, the Township has requested calculations for the change in coverage. A response to the Township has been drafted and is undergoing legal review.

## FOOTNOTE language
14-1 | Notes: N/A = not applicable (no additional follow-up is necessary, or the Project does not cross FEMA floodplains) NR = no response received to date; stormwater management analysis and floodplain management analysis is provided in municipality correspondences TBD = to be determined; correspondence is ongoing * = summary of follow-up correspondence provided in attached Table 14-2 ** = County has authority to enforce floodplain/stormwater management regulations
14-2 | Notes: N/A = not applicable (no additional follow-up is necessary, or the Project does not cross FEMA floodplains) NR = no response received to date; stormwater management analysis and floodplain management analysis is provided in municipality correspondences TBD = to be determined; correspondence is ongoing ** = County has authority to enforce floodplain/stormwater management regulations