## Existing CSOs
Permit No. | Facility Name | Status | Major or Minor | Fee Category | County | Region | Municipality | Latest Permit Issuance Date | Permit Effective Date | Permit Expiration Date1 | Client | Facility Address | No. of CSO Outfalls | NMC Received Date2 | LTCP Received Date2 | LTCP Latest Approved Date2 | LTCP Completion Date2 | Comments | LTCP Approach | Enforcement Actions | Comments/Status
PA0020125 | MONACA BORO STP | Active | Major | Major Sewage Facility with CSO | Beaver | SWRO | Monaca Boro | 2017-08-22 | 2017-09-01 | 2022-08-31 | MONACA BORO BEAVER CNTY | 928 PENNSYLVANIA AVE, MONACA, PA 15061-1800 | 6 | 2004-01-15 | 2006-02-03 | 2007-08-23 | 2007-08-23 | LTCP completed, PCCMP approval and implementation pending 4 of 6 outfalls capped and inactive | Presumption (85% capture) |  | LTCP Presumption approved by DEP. Permitte claims with separation and conveyance increases now at > 85% capture and 3 of 7 outfalls are now closed. EPA required the submission of a Post-Construction Compliance Monitoring Plan (PCCMP). Revised PCCMP submission review pending. The upgraded sewage treatment plant came online in August 2015. The new plant was designed with sufficient capacity to handle peak flows. Upgrades to the City’s two pump stations (Pine Street and Clark Street) were also completed by August 2015. To date, there have been no discharges from a CSO since these upgrades were completed.
PA0020346 | PUNXSUTAWNEY BORO STP | Active | Major | Major Sewage Facility with CSO | Jefferson | NWRO | Punxsutawney Boro | 2013-06-12 | 2013-07-01 | 2018-06-30 | PUNXSUTAWNEY BORO JEFFERSON CNTY | SUITE 1, 301 EAST MAHONING STREET, PUNXSUTAWNEY, PA 15767 | 4 | 2000-10-11 | 2000-11-27 | 2005-02-16 | TBD | Reporting 93.9% capture. | Presumption (85% capture) |  | The % capture methodology is included in the revised approved LTCP. Data has been submitted showing 85% capture has been achieved. In-stream monitoring is being conducted as part of post-construction monitoring. No CSO outfalls above drinking water intakes. STP takes brine from a privately-owned entity with a pretreatment system hard-piped into the STP.
PA0020397 | BRIDGEPORT BORO STP | Active | Minor | Minor Sewage Facility with CSO | Montgomery | SERO | Bridgeport Boro | 2022-06-03 | 2022-07-01 | 2027-06-30 | BRIDGEPORT BORO MONTGOMERY CNTY | PO BOX 148, BRIDGEPORT, PA 19405-0148 | 5 | 2003-01-31 | 2003-10-01 | 2004-05-10 | 2015-05-06 | LTCP update received 2019. Control projects planned through 2027. | Partial Separation / Presumption | Consent Order & Agreement (COA) | COA executed on 11/20/01. CSO inspections on 10/26/05 and 01/02/2008 found the permittee to be in compliance with the NMCs. LTCP end date was provided by the permittee in a 12/26/08 LTCP implementation schedule. Recently four CSO outfalls (002, 003, 004, and 005) were removed. One new CSO outfall (004A) was added. This brings the previous six CSO outfalls to three (001, 004A, and 006).
PA0020613 | WAYNESBURG STP | Active | Minor | Minor Sewage Facility with CSO | Greene | SWRO | Franklin Twp | 2013-02-13 | 2013-03-01 | 2018-02-28 | WAYNESBURG BORO GREENE CNTY | 90 E HIGH ST, WAYNESBURG, PA 15370-1817 | 2 | 2005-01-13 | 2006-03-09 | 2007-08-14 | 2015-12-31 | Revised LTCP approved 9/17/20 | Separation |  | LTCP for sewer separation approved. Separation work underway.
PA0020681 | SEWICKLEY BORO STP | Active | Minor | Minor Sewage Facility with CSO | Allegheny | SWRO | Sewickley Boro | 2011-01-04 | 2011-02-01 | 2016-01-31 | SEWICKLEY BORO ALLEGHENY CNTY | PO BOX 428, 601 THORN ST, SEWICKLEY, PA 15143-0428 | 5 | 1995-11-19 | 2008-01-23 | 2009-07-28 | 2013-12-31 | Completed | Presumption |  | Funding caused a delay in LTCP implementation. PCCMP submission required by permit on 1/31/2013.
PA0020702 | FAYETTE CITY STP | Active | Minor | Minor Sewage Facility with CSO | Fayette | SWRO | Fayette City Boro | 2009-08-03 | 2009-09-01 | 2014-08-31 | FAYETTE CITY BORO MUNI AUTH FAYETTE CNTY | PO BOX 552, FAYETTE CITY, PA 15438-0552 | 2 | 1998-07-07 | 2007-08-30 | 2009-02-11 | 2010-12-31 | LTCP Implementation Incomplete LTCP Revision Possible | Presumption | DEP Enforcement Action | There is a drinking water intake @ Belle Vernon 2.5 mi downstream. The permittee has implemented LTCP improvements and claims they meet 85% capture. PCCMP submission, review and implementation pending.
PA0021113 | GLASSPORT BORO - STP | Active | Major | Major Sewage Facility with CSO | Allegheny | SWRO | Glassport Boro | 2016-11-30 | 2016-12-01 | 2021-11-30 | GLASSPORT BORO ALLEGHENY CNTY | 440 MONONGAHELA AVE, GLASSPORT, PA 15045-1423 | 6 | 2015-01-08 | 2015-03-10 | 2015-04-01 | 2018-04-01 | LTCP milestone implementation ongoing | Presumption (85% capture) |  | LTCP was approved on 4/1/15. The 85% capture / presumption approach is to be implemented by 4/1/18.
PA0021148 | MT PLEASANT BORO STP | Active | Major | Major Sewage Facility with CSO | Westmoreland | SWRO | Mount Pleasant Boro | 2022-02-18 | 2022-03-01 | 2022-11-30 | MUNICIPAL AUTHORITY OF WESTMORELAND COUNTY | 1 ETZE AVENUE, MOUNT PLEASANT, PA 15666 | 3 | 2001-01-26 | 2016-11-02 | 2016-11-07 | 2019-06-01 | Conveyance Capacity System Improvements; transfered to municipal authority in 2022 | Presumption (85% capture) | DEP Enforcement Action | A Notice of Violation (NOV) was sent on 3/1/1999 NOV. A PCCMP is necessary to verify claims of capture compliance.
PA0021237 | NEWPORT STP | Active | Minor | Minor Sewage Facility with CSO | Perry | SCRO | Newport Boro | 2016-12-07 | 2017-01-01 | 2021-12-31 | NEWPORT BORO MUNI AUTH PERRY CNTY | 231 MARKET ST, NEWPORT, PA 17074-1533 | 2 | 1995-06-09 | 1995-06-09 | 2015-06-02 | TBD | 2 CSO outfalls eliminated 2019 & 2020 | Presumption | Consent Order & Agreement (COA) | Currently in process of separating sewers. DEP is negotiating a COA with the permittee that will require them to develop and submit a LTCP. In addition, their headworks-related CSO bypass will be eliminated with an upgrade of the WWTP.
PA0021407 | POINT MARION WWTP | Active | Minor | Minor Sewage Facility with CSO | Fayette | SWRO | Point Marion Boro | 2014-01-13 | 2014-02-01 | 2019-01-31 | POINT MARION BORO MUNI AUTH FAYETTE CNTY | PO BOX 236, POINT MARION, PA 15474-0236 | 6 | 1993-12-01 | 2004-11-04 | 2013-07-24 | 2023-09-01 |  | Separation |  | Additional LTCP development required.
PA0021521 | SMETHPORT BORO AUTH STP | Active | Minor | Minor Sewage Facility with CSO | McKean | NWRO | Smethport Boro | 2017-06-27 | 2017-07-01 | 2022-06-30 | SMETHPORT BORO AUTH MCKEAN CNTY | 201 W WATER ST, SMETHPORT, PA 16749 | 1 | 2001-12-28 | 2002-12-24 | 2006-02-15 | TBD |  | Presumption (4-6 overflows ) |  | The number of CSO discharge events has been reduced to less than 4 per year. An NPDES permit renewal has changed the designation of the former CSO outfall (002) to a CSO-related bypass (IMP 101). This is due to construction of new fine screens, that were located before the CSO bypass.
PA0021610 | BLAIRSVILLE MUNI AUTH STP | Active | Major | Major Sewage Facility with CSO | Indiana | NWRO | Blairsville Boro | 2009-04-17 | 2009-04-17 | 2013-02-28 | BLAIRSVILLE MUNI AUTH INDIANA CNTY | 203 E MARKET ST, BLAIRSVILLE, PA 15717-1120 | 5 | 2002-05-14 | 2007-04-27 | 2007-07-24 | 2010-07-31 | Partial Separation Completed, 5 active CSOs | Separation |  | PCCMP required to verify if the permittee is meeting 85% capture. Eight CSOs outfalls were eliminated, with only 5 remaining.
PA0021687 | WELLSBORO MUN AUTH | Active | Major | Major Sewage Facility with CSO | Tioga | NCRO | Wellsboro Boro | 2022-05-23 | 2022-06-01 | 2027-05-31 | WELLSBORO BORO MUNI AUTH TIOGA CNTY | 28 CRAFTON ST, WELLSBORO, PA 16901-1549 | 2 | 2000-06-14 | 2011-01-01 | 2012-06-04 | TBD (2027 projected) | Revised LTCP to be completed by 12/1/2023; NMCs in full implementation | Presumption |  | In calendar year 2014, Wellsboro reported 12 CSO events.
PA0021814 | MANSFIELD MUNI SEW AUTH | Active | Major | Major Sewage Facility with CSO | Tioga | NCRO | Mansfield Boro | 2021-07-20 | 2021-08-01 | 2026-07-31 | MANSFIELD BORO MUNI AUTH TIOGA CNTY | 14 S MAIN ST, MANSFIELD, PA 16933-1527 | 3 | 1999-09-17 | 2012-11-07 | 2012-11-30 | TBD | LTCP Updated 10/2016; PCCMP to be developed by 2024 | Presumption (85% capture) |  | LTCP update submitted on 11/7/12. The permittee is already meeting 85% capture.
PA0022209 | BEDFORD STP | Active | Major | Major Sewage Facility with CSO | Bedford | SCRO | Bedford Boro | 2021-02-26 | 2021-03-01 | 2026-02-28 | BEDFORD BORO MUNI AUTH | 244 W PENN ST, BEDFORD, PA 15522-1226 | 1 | 2001-03-18 | 2002-07-16 | 2004-06-01 | TBD |  | Presumption | COA | The permittee has completed some extensive line replacements to reduce the amount of infiltration into the system. In 2013 there were no CSO discharges.
PA0022292 | EBENSBURG WWTP | Active | Major | Major Sewage Facility with CSO | Cambria | SWRO | Cambria Twp | 2013-04-10 | 2013-05-01 | 2018-04-30 | EBENSBURG BORO MUNI AUTH CAMBRIA CNTY | 300 WEST HIGH STREET, EBENSBURG, PA 15931 | 1 | 2000-03-30 | 2000-03-30 | 2006-07-13 | 2020-01-01 | Separation completed 2021; PCCMP underway | Separation |  | LTCP approval requires sewer separation by 2014 with 2-year PCCMP. PCCMP devopment and implementation pending.
PA0023167 | PINE STREET STP KANE | Active | Major | Major Sewage Facility with CSO | McKean | NWRO | Kane Boro | 2021-03-19 | 2021-03-19 | 2023-01-31 | PA AMER WATER CO | PO BOX 79, 112 BAYARD ST, KANE, PA 16735-0079 | 1 | 2001-07-16 | 2010-12-03 | 2011-05-09 | Complete |  | CSO-related bypass only |  | LTCP approved with 85% capture approach. During NPDES permit renewal process in 2010, the permittee was asked to verify they are meeting the 85% capture standard for the sewers that are tributary to the Kinzua Rd STP. The data appears they are capturing about 90% of wet weather flows in the Kinzua "sewershed". Inflow and infiltration (I/I) projects to be completed as funding allows. Post-construction monitoring is on-going.
PA0023175 | KINZUA ROAD STP KANE | Active | Major | Major Sewage Facility with CSO | McKean | NWRO | Kane Boro | 2021-03-19 | 2021-04-01 | 2022-01-31 | PA AMER WATER CO | 112 BAYARD ST, KANE, PA 16735-1377 | 2 | 1997-10-09 | 2003-08-29 | 2004-03-18 | Post construction monitoring is on-going. |  | Presumption (85% capture) | COA | The permittee has two active CSOs remaining (Ida St & Iron St). The Ida St CSO to be sealed/eliminated by end of May 2015. Last seperation project has been desinged and split into two phases. Working with PennVEST on funding both project which should take two years. All work is projected to be completed and last CSO eliminated prior to end date of LTCP (2020).
PA0023469 | CTL WAYNE REG AUTH | Active | Major | Major Sewage Facility with CSO | Wayne | NERO | Texas Twp | 2016-12-01 | 2016-12-01 | 2019-05-31 | CTL WAYNE REG AUTH WAYNE CNTY | 574 BUCKS COVE RD, HONESDALE, PA 18431-1143 | 1 | 1996-05-04 | 2005-08-30 | 2007-02-23 | TBD (To Be Determined) | revised LTCP for remaining CSO outfall submitted 2014 | Partial Separation / Presumption |  | Discharges to an abandoned mine drainage (AMD) impacted stream. An updated LTCP was required by 2013.
PA0023558 | ASHLAND BOROUGH WWTP | Active | Major | Major Sewage Facility with CSO | Schuylkill | NERO | Ashland Boro | 2012-04-23 | 2012-05-01 | 2017-04-30 | ASHLAND BORO COLUMBIA & SCHUYLKILL CNTY | 401 S 18TH ST, ASHLAND, PA 17921-1748 | 7 | 2001-03-20 | 2003-02-06 | 2003-06-10 | TBD | LTCP updated 2016 | Demonstration (85% load reduction) |  | Permittee claims they are meeting 85% capture. A PCCMP is due 24 months following the latest permit issuance date.
PA0023701 | MIDLAND BORO STP | Active | Major | Major Sewage Facility with CSO | Beaver | SWRO | Midland Boro | 2014-06-12 | 2014-07-01 | 2019-06-30 | MIDLAND BORO MUNI AUTH BEAVER CNTY | 10TH ST & RAILROAD AVE, MIDLAND, PA 15059 | 1 | 1996-03-29 | 2003-06-02 | 2013-01-24 | Completed | PCCMP Submission and Implementation Pending | Presumption |  | An updated LTCP was received by DEP on 1/10/2013.
PA0023736 | TRI-BORO MUN AUTH | Active | Minor | Minor Sewage Facility with CSO | Susquehanna | NERO | Susquehanna Depot Boro | 2021-07-13 | 2021-08-01 | 2026-07-31 | TRI BORO MUNI AUTH SUSQUEHANNA CNTY | 83 ERIE BLVD., SUSQUEHANNA, PA 18847 | 2 | 1999-03-09 | 2001-03-15 | 2001-04-09 | 2041-12-31 | Final LTCP due June 2024; PCCMP due June 2025 | Presumption |  | Sewer separation and conveyance capacity improvements completed. PCCMP submission and implementation pending.
PA0024490 | ROCKWOOD BORO STP | Active | Minor | Minor Sewage Facility with CSO | Somerset | SWRO | Rockwood Boro | 2014-06-18 | 2014-07-01 | 2019-06-30 | ROCKWOOD BORO MUNI AUTH SOMERSET CNTY | 669 SOMERSET AVE, ROCKWOOD, PA 15557-1034 | 2 | 2007-02-22 | 2006-01-19 | 2007-08-17 | 2008-12-31 | PCCMP Still needed | Presumption (4-6 overflows ) |  | COA issued for LTCP implementation. Presumption Approach proposed with combination of separation and treatment improvements. Construction complete.
PA0024589 | LEETSDALE MUN AUTH STP | Active | Minor | Minor Sewage Facility with CSO | Allegheny | SWRO | Leetsdale Boro | 2016-03-14 | 2016-04-01 | 2021-03-31 | LEETSDALE BORO MUNI AUTH ALLEGHENY CNTY | 5 6TH ST, LEETSDALE, PA 15056-1303 | 4 | 2004-04-28 | 2006-02-09 | 2006-04-07 | 2011-04-25 | LTCP Completed, PCCMP approval and implementation pending. | Presumption | COA | CSOs discharge to an AMD impacted stream. LTCP proposes partial sewer replacement, CSO modifications/improvements, and WWTP expansion. Substantially complete as of March 2013.
PA0024716 | FREELAND BORO MUN AUTH | Active | Major | Major Sewage Facility with CSO | Luzerne | NERO | Foster Twp | 2016-09-19 | 2016-10-01 | 2021-09-30 | FREELAND BORO MUNI AUTH LUZERNE CNTY | 711 BIRKBECK ST, FREELAND, PA 18224-1501 | 1 | 2001-03-26 | 2009-05-28 | 2009-08-27 | TBD | updated LTCP submitted 02/2017 | Presumption |  | Next NPDES renewal targeted to require submittal of updated LTCP.
PA0025224 | ST CLAIR WWTP | Active | Minor | Minor Sewage Facility with CSO | Schuylkill | NERO | East Norwegian Twp | 2015-12-09 | 2013-05-28 | 2020-12-31 | SAINT CLAIR BORO SEW AUTH SCHUYLKILL CNTY | 16 S 3RD ST, SAINT CLAIR, PA 17970-1207 | 6 | 1996-01-10 | 2002-09-09 | 2020-09-11 | 2037-03-01 | Implementing monitoring to plan improvements | No LTCP Approach |  | Small Community exemption revoked. One outfall authorization revoked and closed. Permittee claims they are meeting 85% capture. Renewed permit requires Final Phase II LTCP Proposals by 12/1/17.
PA0025755 | FREEPORT BORO STP | Active | Minor | Minor Sewage Facility with CSO | Armstrong | NWRO | Freeport Boro | 2021-12-17 | 2022-01-01 | 2026-12-31 | FREEPORT BORO ARMSTRONG CNTY | 414 MARKET ST, FREEPORT, PA 16229-1122 | 5 | 2000-05-16 | 2001-05-21 | 2004-02-12 | 2025-10-01 | Phase II LTCP to be constructed by 6/1/25. PCCMP submitted by 10/1/25 | Presumption (85% capture) |  | COA executed and Presumption Approach approved. Sytem improvements and PCCMP implementation reqirements underway.
PA0025950 | MONONGAHELA CITY STP | Active | Major | Major Sewage Facility with CSO | Washington | SWRO | Monongahela City | 2013-10-09 | 2013-11-01 | 2018-10-31 | MONONGAHELA CITY MUNI AUTH WASHINGTON CNTY | 521 W MAIN ST, MONONGAHELA, PA 15063-2615 | 1 | 2000-06-07 | 2007-11-16 | 2009-09-22 | 2014-12-31 | LTCP Completed, PCCMP approval and implementation pending. | Presumption | COA | DEP and EPA are meeting with ALCOSAN routinely to provide guidance on wet weather plan development. The agencies are also preparing guidelines for customer municipalities to develop their feasibility studies.
PA0025984 | ALCOSAN SEW SYS | Active | Major | Major Sewage Facility with CSO | Allegheny | SWRO | Pittsburgh City | 2020-07-23 | 2020-07-23 | 2023-12-31 | ALLEGHENY CNTY SANI AUTH ALCOSAN | 3300 PREBLE AVE, PITTSBURGH, PA 15233-1025 | 254 | 1996-10-01 | 2013-07-31 | 2018-12-01 | 2036-09-30 | GI, Conveyance Capacity and Treatment Capacity Improvements | Demonstration | EPA/DEP Enforcement Action Finalized | Updated LTCP approved on 10/15/10. Water Quality Management Permit for relocation and reconstruction of CSO Outfall 004 was issued on 12/12/12.
PA0026042 | BETHLEHEM CITY WWTP | Active | Major | Major Sewage Facility with CSO | Northampton | NERO | Bethlehem City | 2012-12-12 | 2013-01-01 | 2013-11-30 | BETHLEHEM CITY NORTHAMPTON CNTY | 10 EAST CHURCH STREET, BETHLEHEM, PA 18018 | 2 | 1996-11-07 | 2009-09-01 | 2010-10-15 | TBD |  | Demonstration |  | A total of eight CSO outfall have been eliminated. CSO Outfall 020 cannot be sealed until the completion of the Phase I component of the LTCP, expected to be completed no later than 12/1/19, as stated in the COA.
PA0026069 | LATROBE MUNIC AUTH STP | Active | Major | Major Sewage Facility with CSO | Westmoreland | SWRO | Latrobe Boro | 2017-09-08 | 2017-10-01 | 2022-09-30 | LATROBE MUNI AUTH WESTMORELAND CNTY | PO BOX 88, LATROBE, PA 15650-0088 | 12 | 1999-07-01 | 2016-03-01 | 2016-05-25 | 2019-12-01 | Phase I Improvements Underway | Presumption (85% capture) | COA | Updated LTCP received 7/6/2009. Completed diversion chamber and pump station upgrades including metering and SCADA system to maximize flow to WWTP. Rehabilitated old primary settling tanks to bring them on line during wet weather events. Completed Phase I Ross Street sewer separation project. Phase II targeted for 2011. Various other projects plannned or under consideration thoughout service area.
PA0026107 | WYOMING VLY SAN AUTH | Active | Major | Major Sewage Facility with CSO | Luzerne | NERO | Hanover Twp | 2010-06-07 | 2010-06-07 | 2013-02-28 | WYOMING VALLEY SANI AUTH | PO BOX 33A, WILKES BARRE, PA 18703-1333 | 51 | 1993-12-01 | 2000-11-09 | 2000-11-27 | TBD |  | Demonstration |  | Multi-municipal COA executed and amended to required certain LTCP submissions. LTCP was submitted in December 2011 and approved in March 2013. PCCMP still due following LTCP implementation.
PA0026140 | ROCHESTER AREA JT SEW AUTH - STP | Active | Major | Major Sewage Facility with CSO | Beaver | SWRO | Rochester Boro | 2011-02-17 | 2011-03-01 | 2016-02-29 | ROCHESTER BORO AREA JT SEW AUTH BEAVER CNTY | 395 ADAMS ST, ROCHESTER, PA 15074-2128 | 3 | 1996-08-12 | 2011-12-16 | 2017-05-31 | Fall 2022 | Final LTCP task completion of WWTP improvements | Presumption | COA | A COA was executed on 8/21/02 for LTCP and cessation of bypasses. Some legal issues for LTCP implementation arose, LTCP extension expected. PCCMP submission pending.
PA0026158 | MON VLY SEW AUTH STP | Active | Major | Major Sewage Facility with CSO | Washington | SWRO | Carroll Twp | 2014-10-24 | 2014-11-01 | 2019-10-31 | MON VLY SEW AUTH | 20 S WASHINGTON ST, DONORA, PA 15033-1394 | 21 | 2003-02-03 | 2003-01-06 | 2008-04-30 | 2019-04-30 | Underway | Presumption | DEP Enforcement Action | Permittee has four remaining CSO outfalls and is undergoing post-construction monitoring.
PA0026174 | FRANKLIN CITY STP | Active | Major | Major Sewage Facility with CSO | Venango | NWRO | Franklin City | 2009-06-30 | 2009-07-01 | 2014-06-30 | FRANKLIN CITY GEN AUTH VENANGO CNTY | 430 13TH ST, FRANKLIN, PA 16323 | 5 | 2000-03-20 | 2009-01-15 | 2009-03-20 | Implementing PCCMP |  | Presumption (85% capture) |  | CSOs are at the pump station and at the STP. This permit has CSO monitoring requirements in NPDES permit.
PA0026182 | LANSDALE BORO STP | Active | Major | Major Sewage Facility with CSO | Montgomery | SERO | Lansdale Boro | 2021-07-13 | 2021-08-01 | 2026-07-31 | LANSDALE BORO MONTGOMERY CNTY | 1 VINE ST, SUITE 201, LANSDALE, PA 19446-3601 | 2 | 1997-01-08 | 3/20/98, 12/29/00, and 12/11/11 | 7/28/2000 Amendment approved after 12/13/2011 | Complete | PCCMP Ongoing | Presumption
PA0026191 | HUNTINGDON STP | Active | Major | Major Sewage Facility with CSO | Huntingdon | SCRO | Huntingdon Boro | 2017-02-16 | 2017-03-01 | 2022-02-28 | HUNTINGDON BORO HUNTINGDON CNTY | PO BOX 592, HUNTINGDON, PA 16652-0592 | 5 | 1998-04-06 | 1999-03-19 | 1999-04-26 | TBD | 1 CSO outfall eliminated in 2012 | Presumption |  | The LTCP consists of a 20-year 9-phase program to achieve compliance. DEP's approval was for Phases 1 through 3 only. Work beyond Phase 3 is considered tentative and may be adjusted pending Phase 3 monitoring results. Phase 3 monitoring is scheduled to be completed in 2014.
PA0026204 | OIL CITY STP | Active | Major | Major Sewage Facility with CSO | Venango | NWRO | Oil City City | 2013-12-03 | 2014-01-01 | 2018-12-31 | OIL CITY CITY VENANGO CNTY | 21 SENECA STREET, OIL CITY, PA 16301-1379 | 13 | 1996-11-08 | 2004-12-30 | 2006-01-04 | TBD |  | Presumption (85% capture) | COA | The permittee has removed 49 of the previous 54 CSO outfalls and is conducting post-construction monitoring.
PA0026301 | ERIE CITY STP | Active | Major | Major Sewage Facility with CSO | Erie | NWRO | Erie City | 2016-06-22 | 2016-06-22 | 2018-06-30 | ERIE CITY SEW AUTH ERIE CNTY | 68 PORT ACCESS RD, ERIE, PA 16507-2204 | 5 | 2000-09-12 | 2001-05-01 | 2001-10-01 | 2013-12-01 | 1 CSO outfall eliminated (4 remain active) | Presumption |  | Two of six CSO outfalls have been eliminated. Of the four remaining outfalls, three will remain CSO outfalls and one will be a sanitary sewer overflow (SSO), subject to stipulated penalties for discharges. A revised LTCP was received 2/3/14.
PA0026310 | CLEARFIELD MUN SEW SYS STP | Active | Major | Major Sewage Facility with CSO | Clearfield | NCRO | Lawrence Twp | 2009-07-20 | 2009-07-20 | 2013-01-31 | CLEARFIELD MUNI AUTH CLEARFIELD CNTY | 107 E MARKET ST, CLEARFIELD, PA 16830-2405 | 4 | 1998-07-01 | 2014-01-31 | 2014-09-30 | TBD | Updated LTCP with PCCM to be completed by 6/30/2025 | Presumption (85% capture) | COA | CSOs discharge to an AMD impacted stream. Fourteen of the twenty-seven CSO outfalls have been eliminated. The submission of an updated LTCP was required by 6/30/14.
PA0026361 | LOWER LACKAWANNA VALLEY SANITARY AUTHORITY | Active | Major | Major Sewage Facility with CSO | Luzerne | NERO | Duryea Boro | 2021-09-23 | 2021-10-01 | 2026-09-30 | LOWER LACKAWANNA VALLEY SANI AUTH | PO BOX 2067, 398 COTTON ROAD, DURYEA, PA 18642-0067 | 14 | 1995-03-08 | 2004-02-17 | 2021-10-01 | 2041-12-31 | Final LTCP due by 6/30/2024 | Presumption |  | CSOs discharge to an AMD impacted stream. The submission of an updated LTCP was required by 1/31/16.
PA0026476 | COALDALE LANSFORD SUMMIT HLL SEW | Active | Major | Major Sewage Facility with CSO | Schuylkill | NERO | Coaldale Boro | 2013-01-31 | 2013-02-01 | 2018-01-31 | COALDALE-LANSFORD-SUMMIT HILL SEWER AUTHORITY | 124 WEST RIDGE ST, LANSFORD, PA 18232-1310 | 6 | 1998-12-10 | 2004-05-10 | 2005-11-02 | TBD | Updated LTCP submitted 2016 | Presumption |  | Under EPA Administrative Order. EPA & DEP reviewed draft LTCP & provided comments on 9/14/2012. Final LTCP due 12/1/2012. LTCP calls for construction of storage facilities at multiple CSO locations. BNR upgrade of WWTP under construction with substantial completion due 8/1/2014. 7 of its outfall have flow meter installed.
PA0026492 | PA AMERICAN WATER COMPANY SCRANTON WWTP | Active | Major | Major Sewage Facility with CSO | Lackawanna | NERO | Scranton City | 2019-11-27 | 2019-12-01 | 2021-11-30 | PA AMER WATER CO | 800 WEST HERSHEY PARK DRIVE, HERSHEY, PA 17033 | 80 | 1998-11-12 | 1999-12-21 | 2000-06-21 | 2037-12-31 | EPA Consent Decree under Civil Action No. 3:CV-09-1873, requires the implementation of the LTCP by 2037 and the contruction of in-line storage or other modifications to reduce CSO activitations with approximately 74 projects broken up into 5 completion phases | Presumption | EP Enforcement Action | LTCP scheduled to end January 2023 with completion of Phase V. Two (2) CSOs eliminated after completion of Hill Separation Project (2011). Four (4) active CSOs remain. Authority has begun flow characterization which will take 4 years. It is in compliance with it's LTCP schedule. In compliance with NMCs. Authority continues flow study which will be complete in 2016. At that time the system will be evaluated. Authority has completed two projected in 2014 not part of CSO LTCP as part of flood mitigation. Both project removed stormwater from the collection system.
PA0026557 | SUNBURY MUNI AUTH STP | Active | Major | Major Sewage Facility with CSO | Northumberland | NCRO | Sunbury City | 2008-01-18 | 2008-02-01 | 2013-01-31 | SUNBURY CITY MUNI AUTH NORTHUMBERLAND CNTY | 462 S 4TH ST, SUNBURY, PA 17801-3134 | 4 | 1998-12-30 | 2001-03-31 | 2008-03-20 | 2023-01-01 | LTCP Compliance complete; update to PCCMP pending | Presumption (85% capture) |  | 11/20/03 Order for LTCP sent.
PA0026581 | SCOTTDALE STP | Active | Major | Major Sewage Facility with CSO | Westmoreland | SWRO | East Huntingdon Twp | 2013-10-15 | 2013-11-01 | 2018-10-31 | WESTMORELAND FAYETTE MUNI SEW AUTH | PO BOX 126, SCOTTDALE, PA 15683-0126 | 8 | 1999-03-16 | 2004-12-03 | 2013-07-23 | 2015-03-21 | LTCP update submitted 8/2020, PCCMP approval and implementation pending | Presumption | DEP Enforcement Action | We met with PWD on 1/5/06 and on 1/11/06 to discuss the facility LTCP update. A 3/11/2008 inspection found the facility in compliance with the NMCs. We are actively reviewing and meeting with EPA and PWD to finalize their update LTCP. On 7/1/2011 DEP recognized a LTCPU (updated LTCP).
PA0026662 | PHILA WATER DEPT - SOUTHEAST WPC PLANT | Active | Major | Major Sewage Facility with CSO | Philadelphia | SERO | Philadelphia City | 2007-08-15 | 2007-09-01 | 2012-08-31 | PHILA WATER DEPT | 1101 MARKET ST, 5TH FLOOR, PHILADELPHIA, PA 19107-2994 | 34 | 1996-12-27 | 1997-01-24 | 1997-09-18 | 2029-09-01 |  | Presumption | COA executed on 8/4/2008 & 7/1/11 | We met with PWD on 1/5/06 and on 1/11/06 to discuss the facility LTCP update. A 03/11/2008 inspection found the facility in compliance with NMCs. We are actively reviewing and meeting with EPA and PWD to finalize their update LTCP. On 7/1/2011 DEP recognized a LTCPU (updated LTCP).
PA0026671 | PHILA WATER DEPT - SOUTHWEST WPC PLANT | Active | Major | Major Sewage Facility with CSO | Philadelphia | SERO | Philadelphia City | 2007-08-15 | 2007-09-01 | 2012-08-31 | PHILA WATER DEPT | 1101 MARKET ST, 4TH FLOOR, PHILADELPHIA, PA 19107-2994 | 75 | 1996-12-27 | 1997-01-24 | 1997-09-18 | 2029-09-01 |  | Presumption | COA executed on 8/4/2008 & 7/1/11 | A 9/11/02 CSO inspection found PWD to be in compliance with the NMCs. A 11/4/05 CSO inspection found PWD in compliance with NMCs. Also, we met with PWD on 1/5/06 and again on 1/11/06 to discuss update of their LTCP. A 3/11/08 inspection found the facility in compliance also. We are activly reviewing and meeting with EPA and PWD to finalize their Update LTCP. On 7/1/2011 DEP recognized a LTCPU (updated LTCP).
PA0026689 | PHILA WATER DEPT - NORTHEAST WPC PLANT | Active | Major | Major Sewage Facility with CSO | Philadelphia | SERO | Philadelphia City | 2007-08-15 | 2007-09-01 | 2012-08-31 | PHILA WATER DEPT | 1101 MARKET STREET, 5TH FLOOR, PHILADELPHIA, PA 19107-2994 | 57 | 1996-12-27 | 1997-01-24 | 1997-09-18 | 2029-09-01 |  | Presumption | COA executed on 8/4/2008. A new COA excuted on 7/1/2011. | Chesapeake Bay Phase 1 facility. EPA issued Order on 9/5/08 to update LTCP which was accomplished on 7/09. The LTCP is again being updated as part of the Act 537 Plan. Lancaster is doubling the size of the North Pump Station to accommodate CSO Flows. EPA is suggesting they incorporate green infrastructure in their update LTCP.
PA0026743 | LANCASTER CITY STP | Active | Major | Major Sewage Facility with CSO | Lancaster | SCRO | Lancaster City | 2012-06-18 | 2012-06-18 | 2015-07-31 | LANCASTER CITY LANCASTER CNTY | 120 N DUKE ST, LANCASTER, PA 17608 | 5 | 1996-12-23 | 1998-09-21 | 2010-01-01 | TBD |  | Demonstration | EPA Consent Decree executed 2/27/2018. | Additional model calibration required for engineering design considerations.537 Facilities planning issues identified, PCSA wants to pull out of system delaying resolution of 537 issues. City of Clairton sewer system work must be undertaken to close unauthorized discharge locations. Copermit with the City of Clairton with enforcement document pending evaluation of City of Clairton illegal CSO outfalls being transferred to the Authority.
PA0026824 | CLAIRTON MUN AUTH STP | Active | Major | Major Sewage Facility with CSO | Allegheny | SWRO | Clairton City | 2021-12-13 | 2022-01-01 | 2026-12-31 | CLAIRTON CITY MUNI AUTH ALLEGHENY CNTY | 1 N STATE ST, CLAIRTON, PA 15025-2172 | 5 | 2002-12-23 | 2007-06-18 | 2007-12-11 | 2026-07-01 | MBR Technology Approved; Phase 2 STP Construction to begin by 11/30/23 | Presumption |  | LTCP calls for Presumption Approach and completion of pending PCCMP by 8/1/2017. Elimination of a majority of outfalls. 2011, LTCP revision approved for the construction of storage tank approved for dischrges to sensitive areas.
PA0026891 | CHARLEROI BORO AUTH STP | Active | Major | Major Sewage Facility with CSO | Washington | SWRO | Charleroi Boro | 2013-11-18 | 2013-12-01 | 2018-11-30 | CHARLEROI BORO AUTH WASHINGTON CNTY | PO BOX 211, CHARLEROI, PA 15022-0211 | 10 | 1998-12-12 | 2007-01-09 | 2007-08-07 | 8/30/2014-1/11/2017 | LTCP Underway | Presumption | COA | 3/1/99 NOV sent, Revised LTCP states in compliance (captures 94% of flow). Needs to evaluate the 94% number before LTCP approval-awaiting proof. Addresses the Sensitive Areas recreational swimming and boating requirements within the Yough River Park area by proposing facilities to nearly eliminate CSO discharges at outfalls 004, 005 and 006. CMA proposes to accomplish this by modifying these regulator structures; by upgrading the West Side interceptor to a minimum of 27 inches diameter and by increasing the West Side pump station capacity to 11.4 mgd; by providing variable frequency drives; by installing an emergency generator and; by providing SCADA monitor data for remote real-time control. Permanently seal CSO outfall 007 and eliminate CSO outfall 003 by constructing a new 24-inch diameter parallel interceptor from CSO outfall 017, terminating into a 36-inch diameter interceptor that will convey flow directly into the WWTP influent.
PA0026905 | CONNELLSVILLE STP | Active | Major | Major Sewage Facility with CSO | Fayette | SWRO | Connellsville City | 2004-01-13 | 2004-02-01 | 2009-01-31 | CONNELLSVILLE CITY MUNI AUTH FAYETTE CNTY | PO BOX 925, CONNELLSVILLE, PA 15425-0925 | 16 | 2004-12-29 | 2004-08-30 | 2017-08-07 | 2021-04-21 |  | Presumption (85% capture) | EPA Order | 537 Planning and LTCP approval for Pressumption Approach. LTCP completion required 70 months following Part II construction permit approval. Part II construction permit issued and construction underway. According to Fact Sheet for the draft permit issued on July 20, 2015 the Authority was granted a Part 2 WQM Permit on July 27, 2010 for the expansion of the plant to treat wet weather combined flows of up to 56MGD and average daily (dry weather) flows of 13MGD. Construction of the expanded plant is to be completed by July of 2015. The Authority appears on track to make this deadline.
PA0026913 | MCKEESPORT STP | Active | Major | Major Sewage Facility with CSO | Allegheny | SWRO | McKeesport City | 2018-01-24 | 2018-02-01 | 2023-01-31 | PA AMER WATER CO | 100 ATLANTIC AVE, MCKEESPORT, PA 15132-3807 | 30 | 2002-11-01 | 2004-04-30 | 2008-11-08 | 2016-12-31 | PCCMP submission Pending | Presumption | CAO following PAWC Purchase | AMD affected stream. Installed vortex separators at Outfalls 002 and 003. Maximize flow to plant. Construction of WWTP improvements scheduled for substantial completion by December 2011.
PA0026921 | GR HAZLETON JT SEW AUTH WWTP | Active | Major | Major Sewage Facility with CSO | Luzerne | NERO | Hazleton City | 2022-02-03 | 2022-03-01 | 2027-02-28 | GREATER HAZLETON CITY JT SEW AUTH LUZERNE CNTY | PO BOX 651, HAZLETON, PA 18201-0651 | 14 | 2001-01-24 | 2002-09-20 | 2003-05-07 | TBD | Final revised LTCP by 3/1/2026 | Presumption |  | Regional consolidation occurred and system is under ownership of the City of McKeesport M.A. Permit issuance pending MACM review of LTCP options and eventual LTCP approval.
PA0026981 | DUQUESNE STP | Active | Major | Major Sewage Facility with CSO | Allegheny | SWRO | Duquesne City | 2003-09-05 | 2003-10-01 | 2008-09-05 | PA AMER WATER CO | 100 ATLANTIC AVE, MCKEESPORT, PA 15132-3807 | 4 | 2001-07-17 | 2008-09-24 | 2009-02-17 | 2023-03-01 |  | Presumption |  | NPDES renewal issued 12/7/2011 requires submittal of Updated LTCP within one year of effective date.
PA0027006 | TAMAQUA BORO | Active | Major | Major Sewage Facility with CSO | Schuylkill | NERO | Walker Twp | 2011-12-07 | 2012-01-01 | 2016-12-31 | TAMAQUA BORO SCHUYLKILL CNTY | 320 EAST BROAD STREET, TAMAQUA, PA 18252 | 12 | 2001-02-06 | 2003-02-13 | 2003-06-17 | TBD |  | No LTCP Approach |  | Chesapeake Bay Phase 1 facility. Permit amendment issued 12/10/09.
PA0027014 | ALTOONA EAST STP | Active | Major | Major Sewage Facility with CSO | Blair | SCRO | Altoona City | 2021-09-29 | 2021-10-01 | 2026-09-30 | ALTOONA WATER AUTH | 900 CHESTNUT AVE, ALTOONA, PA 16601-4617 | 1 | 1996-06-03 | 1998-03-25 | 1998-03-25 | 2026-07-01 | Updated LTCP approved 9/20/2020 | Presumption |  | Chesapeake Bay Phase 1 facility. Permit amendment issued 12/10/09.
PA0027022 | ALTOONA WEST STP | Active | Major | Major Sewage Facility with CSO | Blair | SCRO | Altoona City | 2021-09-29 | 2021-10-01 | 2026-09-30 | ALTOONA WATER AUTH | 900 CHESTNUT AVE, ALTOONA, PA 16601-4617 | 1 | 1997-02-19 | 1998-03-25 | 1998-03-25 | 2026-07-01 | Updated LTCP approved 9/20/2020 | Presumption |  | Conditions of the EPA Order have been met. Implementation of Unified Post Construction Monitoring. Meeting 85% Capture.
PA0027049 | WILLIAMSPORT SANITARY AUTHORITY - WEST STP | Active | Major | Major Sewage Facility with CSO | Lycoming | NCRO | Williamsport City | 2017-10-25 | 2017-11-01 | 2022-10-31 | WILLIAMSPORT CITY SANI AUTH LYCOMING CNTY | 253 W 4TH ST, WILLIAMSPORT, PA 17701-6113 | 1 | 2000-03-31 | 2008-01-01 | 2012-11-28 | 2013-11-28 |  | Presumption (85% capture) | EPA Order | Conditions of the EPA Order have been met. Implementation of Unified Post Construction Monitoring. Meeting 85% Capture.
PA0027057 | WILLIAMSPORT SANI AUTH CENTRAL STP | Active | Major | Major Sewage Facility with CSO | Lycoming | NCRO | Williamsport City | 2022-04-13 | 2022-05-01 | 2027-04-30 | WILLIAMSPORT CITY SANI AUTH LYCOMING CNTY | 253 W 4TH ST, WILLIAMSPORT, PA 17701-6113 | 3 | 1998-12-10 | 2008-04-01 | 2012-11-28 | 2013-11-28 | PCCMP implementation by 5/1/2025 | Presumption (85% capture) | EPA Order | Elimated one CSO. Completed various sewer separation, sewer replacement & pump station projects. The 2014 annual CSO report (included with Chapter 94 reports) indicates that Outfall 010 (MH 57) near the D&H railroad bridge in Carbondale is now out of service. This was confirmed in an email from LRBSA, dated April 3, 2014, and the outfall is removed from the permit. Under the presumption approach, the goal of the facility is the elimination or capture for treatment of no less than 85% by volume of the combined sewage collected in the CSS during precipitation events on a system-wide annual average basis. Outfalls 013 and 018 have flow meters that monitor and record overflow data.
PA0027065 | LRBSA - ARCHBALD WWTP | Active | Major | Major Sewage Facility with CSO | Lackawanna | NERO | Archbald Boro | 2015-09-23 | 2015-10-01 | 2020-09-30 | LACKAWANNA RIVER BASIN SEW AUTH | PO BOX 280, OLYPHANT, PA 18447-0280 | 5 | 1999-07-01 | 2000-07-28 | 2000-08-21 | TBD |  | Presumption |  | Eliminated 6 CSOs. Completed various sewer separation, sewer replacement & pump station projects. Installed side stream CSO primary treatment & disinfection system at main CSO.
PA0027081 | LRBSA - CLINTON TWP PLANT | Active | Minor | Minor Sewage Facility with CSO | Wayne | NERO | Clinton Twp | 2016-11-07 | 2016-12-01 | 2021-11-30 | LACKAWANNA RIVER BASIN SEW AUTH | PO BOX 280, OLYPHANT, PA 18447-0280 | 3 | 1999-07-01 | 2000-07-28 | 2000-08-21 | TBD |  | Presumption (85% capture) |  | Elimated 4 CSOs. Completed various sewer separation, sewer replacement & pump station projects. Constructed improvements at Dickson City City CSO including self cleening screen & overflow measurement. Headworks wet weather improvements substantially complete March 2010 & WWTP expansion & upgrade to 10 MGD. 2014 update - Eliminated CSO 002 with successful 10MGD upgrade.
PA0027090 | LRBSA - THROOP PLANT | Active | Major | Major Sewage Facility with CSO | Lackawanna | NERO | Throop Boro | 2016-08-15 | 2016-09-01 | 2021-08-31 | LACKAWANNA RIVER BASIN SEW AUTH | PO BOX 280, OLYPHANT, PA 18447-0280 | 16 | 1999-07-01 | 2000-07-28 | 2000-08-21 | TBD | 2 CSO outfalls sealed/out of service; 1 CSO outfall inactive | Presumption |  | A 9/26/02 CSO inspection found DELCORA to be in compliance with the NMCs. Another inspection was conducted on 11/4/05 and DELCORA was in compliance with NMCs. On 11/13/2007 ion was conducted and was in compliance. On 2/1/2011 DELCORA submitted a revised LTCP to EPA. On 9/14/2011 EPA sent a defficiency letter to DELCORA. By 4/19/12, DELCORA will submit the revised LTCP to EPA. CSO# 006 and 027 are removed as aresult of upgrade of PS and bridge construction.
PA0027103 | DELCORA STP | Active | Major | Major Sewage Facility with CSO | Delaware | SERO | Chester City | 2021-03-08 | 2021-04-01 | 2026-03-31 | DELCORA | 100 EAST FIFTH STREET, P.O.BOX 999, CHESTER, PA 19016-0999 | 26 | 1995-07-19 | 1999-03-30 | 2000-05-22 | EPA is taking lead on LTCP |  | Presumption |  | WQM permit for $20M STP head works expansion for wet flow management approved. The LTCP is required to be completed in three phases on or before December 31, 2032.
PA0027111 | NEW KENSINGTON STP | Active | Major | Major Sewage Facility with CSO | Westmoreland | SWRO | New Kensington City | 2017-06-14 | 2017-07-01 | 2022-06-30 | NEW KENSINGTON CITY MUNI SANI AUTH | 120 LOGANS FERRY RD, NEW KENSINGTON, PA 15068-2004 | 6 | 2010-02-16 | 2004-08-20 | 2016-12-02 | 2032-12-31 |  | Presumption (85% capture) | EPA Enforcement Action | City is still planning to upgrade their WWTP, a ~$20 million dollar project, to virtually eliminate all CSOs. PVEST funding offer has been given; all indications are City will move ahead to construct the new WWTP. As of October 2013, City has received bids for the project (which came in higher than expected). They are planning to "adjust" project and re-bid soon. December 2013 expected to have upgraded WWTP on-line
PA0027120 | WARREN CITY WWTP | Active | Major | Major Sewage Facility with CSO | Warren | NWRO | Warren City | 2017-10-19 | 2017-11-01 | 2022-10-31 | WARREN CITY WARREN CNTY | 318 W 3RD AVE, WARREN, PA 16365-2388 | 4 | 1998-09-14 | 2003-05-01 | 2004-01-14 | TBD | PCCMP developed | Presumption (85% capture) |  | Chesapeake Bay Phase 1 facility. Permit Reissued 12/15/09.
PA0027197 | HARRISBURG AWTF | Active | Major | Major Sewage Facility with CSO | Dauphin | SCRO | Harrisburg City | 2009-12-15 | 2010-01-01 | 2014-12-31 | CAPITAL REGION WATER | 212 LOCUST ST STE 500, HARRISBURG, PA 17101-1510 | 61 | 1997-10-23 | 2001-05-04 | 2003-02-01 | TBD |  | Presumption | EPA Consent Decree | The permit authorizes a CSO related bypass. No CSOs above water supply intakes. NMC and LTCP documents received and approved. Extremely financially distressed community. Completed STP headworks upgrade; much effort expended to maximize flows to STP via NMC measures. The NWRO, at EPA's urging, asked Farrell to adopt the 85% capture presumptive approach as a new LTCP endpoint. Farrell did adopt that approach, and will be required to report % capture in future Ch. 94 reports.
PA0027227 | FARRELL MUN SEW | Active | Major | Major Sewage Facility with CSO | Mercer | NWRO | Farrell City | 2012-06-25 | 2012-07-01 | 2017-06-30 | FARRELL CITY MERCER CNTY | 701 MARTIN LUTHER KING JR BOULEVARD, FARRELL, PA 16121 | 3 | 1998-07-17 | 1999-08-18 | 2000-01-05 | TBD |  | Presumption (85% capture) |  | Nine (9) CSOs eliminated with Sprinfield separation project. New WWTP underway, still under construction, to be completed in 2015. COA revised with new completion date for WWTP November 1, 2015. Next seperation ( Phase 3A of LTCP) has been designed/permited and is scheduled for completion at the end of 2017. Currently looking for funding. In compliance with NMCs.
PA0027324 | SHAMOKIN-COAL TWP JT SEW AUTH | Active | Major | Major Sewage Facility with CSO | Northumberland | NCRO | Ralpho Twp | 2020-12-16 | 2021-01-01 | 2025-12-31 | SHAMOKIN & COAL TWP JT SEW AUTH NORTHUMBERLAND CNTY | 114 BRIDGE ST, SHAMOKIN, PA 17872-7690 | 67 | 1996-04-12 | 2002-09-20 | 2008-02-20 | 2042-12-01 | Revised LTCP to be submitted 2023 | Presumption (85% capture) | COA | EPA order converted into a AOC for a coordinated LTCP submittal with customer municipalities.
PA0027391 | UPPER ALLEGHENY JT SANI AUTH STP | Active | Major | Major Sewage Facility with CSO | Allegheny | SWRO | East Deer Twp | 2010-08-05 | 2010-09-01 | 2015-08-31 | UPPER ALLEGHENY JT SANI AUTH | 320 FOURTH AVENUE, TARENTUM, PA 15030-0431 | 19 | 1999-09-01 | 9/3/2003-10/17/2017 | 2018-03-22 | 2025-01-01 |  | TBD | EPA Enforcement Action | The Borough's NPDES permit renewal requires continued implementation of the NMC and implementation of the LTCP. A COA was executed on 3/18/03 which requires NMWA to implement an I/I program and to implement the approved CSO LTCP alternative. The 11/14/05 and 01/02/2008 inspections found the facility in compliance with the NMCs. Portions of the CO & A relating to the implementation of an I/I abatement program and work to be performed in accordance with the LTCP, specifically, evaluation of cost effectiveness of I/I removal and recommendation of I/I removal methods, would require extensive use of closed-circuit televising of the collection system. As a result, the CO & A was amended August 27, 2008, to include revised I/I abatement schedule requirements, reporting requirements, and continued CSO LTCP/NMC requirements. CSO 005 no longer operational.
PA0027421 | NORRISTOWN MUNI STP | Active | Major | Major Sewage Facility with CSO | Montgomery | SERO | Norristown Boro | 2018-10-02 | 2018-11-01 | 2023-10-21 | NORRISTOWN MUNI WASTE AUTH MONTGOMERY CNTY | 235 E AIRY ST, 2ND FLOOR, NORRISTOWN, PA 19401 | 1 | 1996-12-27 | 2001-10-31 | 2002-03-05 | No end date |  | Separation | COA | Revised LTCP approved. Final Permit issued after recent approved LTCP. WQM permit issued for expansion of peak flow capacity. COA.prepared for signatures.
PA0027430 | JEANNETTE STP | Active | Major | Major Sewage Facility with CSO | Westmoreland | SWRO | Jeannette City | 2016-09-09 | 2016-09-09 | 2017-06-30 | WESTMORELAND CNTY MUNI AUTH | 124 PARK N POOL DR, NEW STANTON, PA 15672-2404 | 5 | 2003-11-03 | 8/7/2009 - 4/12/2018 | 2011-08-31 | 2016-12-31 | LTCP Revision Submission Review Underway | Presumption | EPA Enforcement Action | Presumption Approach facilities installed (85% capture), PCCMP submission review pending to evaluate capture ratio. A necessary WQ Criteria component was not provided in PCCMP submission on 3/2013. Reviewed PCCMP asked for more information.
PA0027456 | GREATER GREENSBURG STP | Active | Major | Major Sewage Facility with CSO | Westmoreland | SWRO | Hempfield Twp | 2014-12-19 | 2015-01-01 | 2019-12-31 | GREATER GREENSBURG CITY SEW AUTH WESTMORELAND CNTY | PO BOX 248, GREENSBURG, PA 15601-0248 | 37 | 1997-09-22 | 1998-10-01 | 2003-06-21 | Completed | LTCP completed, PCCMP approval and implementation pending. | Presumption |  | Upon completion of the Leechburg Borough Separation Project (WQM 031440) Outfalls 004, 005, 006, 008, 010, 011, 012 and 015 will be closed and removed from permit. 13 outfalls will remain. LTCP approved and implementation to begin. Several of its Customer Municipalities persuing separation options.
PA0027626 | KISKI VLY WPCA STP | Active | Major | Major Sewage Facility with CSO | Westmoreland | SWRO | Allegheny Twp | 2012-01-25 | 2012-02-01 | 2017-01-31 | KISKI VALLEY WATER POLL CONTROL AUTH | 1361 SCHOOL RD, LEECHBURG, PA 15656-4904 | 21 | 1998-09-28 | 2004-08-12 | 2008-05-22 | Completed | LTCP completed, PCCMP approval and implementation pending. | Presumption |  | Part II permit approved and Pennvest application for system improvements underway. Replacement interceptor and reconstructed outfalls approved. PCCMP submission and review folllows LTCP implementation.
PA0027651 | W NEWTON BORO STP | Active | Minor | Minor Sewage Facility with CSO | Westmoreland | SWRO | West Newton Boro | 2013-06-10 | 2013-07-01 | 2018-06-30 | WEST NEWTON BORO WESTMORELAND CNTY | 112 S WATER ST, WEST NEWTON, PA 15089-1364 | 13 | 2005-07-05 | 2008-02-28 | 2009-04-02 | 2011-12-01 | LTCP completed, PCCMP approval and implementation pending. | Presumption | DEP Enforcement Action | Eliminated 3 CSOs through separation & seeking funding for further separation projects. (four remaining CSOs). Final permit requires submission of updated LTCP before December 31, 2014. The updated Long Term Control Plan should include the projected date by which CSO separation will be completed.
PA0027693 | MINERSVILLE SEWER AUTHORITY WWTP | Active | Major | Major Sewage Facility with CSO | Schuylkill | NERO | Minersville Boro | 2021-07-13 | 2021-08-01 | 2026-07-31 | MINERSVILLE BORO SEW AUTH SCHUYLKILL CNTY | 2 E SUNBURY ST, MINERSVILLE, PA 17954-1719 | 4 | 1999-07-19 | 2004-07-28 | 2004-12-03 | TBD |  | Partial Separation / Presumption |  | LTCP fully approved on 9/12/2002 w/85% capture and post-construction monitoring addressed. Borough has constructed ~$2.5 M worth of projects contained in the approved LTCP, and is currently meeting the 85% capture standard. They are now focusing on needed improvements at the WWTP, as it has become dilapidated & effluent violations persist. DEP as of 4/11/11 signed a new CO&A to ensure the Boro's commitment to upgrade the WWTP. Act 537 for STP upgrades approved May 24, 2012, WQM Permit for upgrades issued 7/11/13. Construction end date will be tracked under the CO&A.
PA0028207 | REYNOLDSVILLE STP | Active | Minor | Minor Sewage Facility with CSO | Jefferson | NWRO | Reynoldsville Boro | 2012-07-19 | 2012-08-01 | 2017-07-31 | REYNOLDSVILLE BORO AUTH JEFFERSON CNTY | PO BOX 207, 400 N 5TH ST, REYNOLDSVILLE, PA 15851-0207 | 7 | 1999-11-30 | 2001-01-16 | 2002-09-12 | TBD |  | Presumption (85% capture) | COA | 4-6 untreated CSOs chosen LTCP endpoint. City recently finished construction of WWTP upgrade, that includes ORFs and a CSO-related bypass as part of its' approved LTCP. August 2009 update -- Post construction stream survey will begin in the near future, as it is the next step required in the CO&A. Future LTCP projects will be driven by the findings of the stream survey. Stream survey has been completed, and DEP is reviewing it to determine any future actions. A CSO inspection will be scheduled soon, to determine how well the NMCs are being implemented, and if the LTCP needs re-visited based on the stream survey findings. City will remain under CO&A for time being. Stream survey to commence in 2011. More LTCP work will be needed. End date not known at this time. / Will evaluate post construction data and stream survey results after they are available.
PA0028223 | CORRY WWTP | Active | Major | Major Sewage Facility with CSO | Erie | NWRO | Corry City | 2019-10-02 | 2019-10-02 | 2019-11-30 | CORRY CITY MUNI AUTH ERIE CNTY | 100 S CENTER ST, CORRY, PA 16407-1923 | 3 | 2000-04-03 | 2002-01-01 | 2002-09-17 | Will evaluate post construction data and stream survey results after they are available. |  | Presumption (4 6 overflows) | COA | 01/01/2000 Permit issued w/ condensed schedule for CSO implementation. LTCP reviewed and not approved. Regional consolidation occurred and system is under ownership of the City of McKeesport M.A. Permit issuance pending MACM review of LTCP options and eventual LTCP approval. Although MACM are a little behind schedule ( DEP met to discuss the schedule late last fall) MACM is still collecting flow data and will then use that information to Update the 537 Plan for their newly expanded service area. Best guess is they will complete that process in conformance with their proposed schedule, then DEP will received the updated537/LTCPs for review.
PA0028401 | DRAVOSBURG BORO STP | Active | Minor | Minor Sewage Facility with CSO | Allegheny | SWRO | Dravosburg Boro | 2018-01-24 | 2018-02-01 | 2023-01-31 | PA AMER WATER CO | 100 ATLANTIC AVE, MCKEESPORT, PA 15132-3807 | 1 | 1998-01-20 | 2008-07-09 | 2014-09-04 | 2024-03-01 |  | Presumption | COA Following PAWC purchase | Final LTCP implementation pending COE lock and dam relocation project. Permit issuance pending. Part II permit for STP upgrades under consideration. PCCM to establish Presumption Approach Criteria underway. Interceptor project completed.
PA0028436 | ELIZABETH BORO STP | Active | Major | Major Sewage Facility with CSO | Allegheny | SWRO | Elizabeth Boro | 2002-08-08 | 2002-09-01 | 2007-08-08 | ELIZABETH BORO MUNI AUTH ALLEGHENY CNTY | 1 LOCUST ST, ELIZABETH, PA 15037-1763 | 6 | 2002-07-01 | 7/7/2004-7/14/17 | 2018-07-12 | 2027-10-31 |  | Presumption |  | As of March 8, 2013 Mid-Cameron continues to meet the presumtive approach.
PA0028631 | MID-CAMERON AUTHORITY | Active | Major | Major Sewage Facility with CSO | Cameron | NCRO | Emporium Boro | 2021-05-26 | 2021-06-01 | 2026-05-31 | MID CAMERON MUNI AUTH | 421 N BROAD ST, EMPORIUM, PA 15834-1401 | 1 | 2003-03-28 | 2005-06-01 | 2005-12-02 | TBD | LTCP last updated 2015 | Presumption |  | Part II Permit # 1114400 issued on May 13, 2014 for combined sewer separation will eliminate CSOs #002 thru 007 when construction complete. DEP is requiring further LTCP review to better evaluate Chesapeake Bay limit and funding availability issues.
PA0036650 | TITUSVILLE WWTP | Active | Major | Major Sewage Facility with CSO | Crawford | NWRO | Titusville City | 2016-10-28 | 2016-11-01 | 2021-10-31 | TITUSVILLE CITY CRAWFORD CNTY | 107 N FRANKLIN ST, TITUSVILLE, PA 16354-1734 | 4 | 1998-10-28 | 2002-03-28 | 2005-03-15 | TBD |  | Presumption (85% capture) | COA signed 10/25/10 | No by-passes in last year. Phase II in future plans if necessary. Meeting 85% capture.
PA0036820 | GALETON BORO WWTP | Active | Minor | Minor Sewage Facility with CSO | Potter | NCRO | Galeton Boro | 2021-07-16 | 2021-08-01 | 2026-07-31 | GALETON BORO AUTH POTTER CNTY | 15 WEST ST, GALETON, PA 16922-1264 | 1 | 2002-08-02 | 2005-03-04 | 2009-03-30 | 2042-01-01 | LTCP last updated 2012; revised update required by 4/1/23 | Presumption (85% capture) |  | LTCP revised for separation. Part II permit for Phase 1 project issued on 09/28/09. Sewer separation complete. PCCMP underway.
PA0037044 | FORD CITY BORO MUNI SEW DISPOSAL AUTH WWTP | Active | Major | Major Sewage Facility with CSO | Armstrong | NWRO | Ford City Boro | 2014-09-09 | 2014-10-01 | 2019-09-30 | FORD CITY BORO MUNI SEW DISPOSAL AUTH | PO BOX 66, FORD CITY, PA 16226-0066 | 3 | 1996-10-25 | 2008-05-01 | 2008-05-06 | 2014-09-28 | Completed | Separation | DEP Enforcement Action | Chesapeake Bay Phase 2 facility.
PA0043273 | HOLLIDAYSBURG REGIONAL STP | Active | Major | Major Sewage Facility with CSO | Blair | SCRO | Frankstown Twp | 2017-02-10 | 2017-03-01 | 2022-02-28 | HOLLIDAYSBURG BORO SEW AUTH BLAIR CNTY | 401 BLAIR ST, HOLLIDAYSBURG, PA 16648-1805 | 3 | 1998-01-05 | 1999-06-30 | 1999-08-30 | TBD | Revised LTCP under Review | Partial Separation / Presumption |  | 32 CSO's eliminated by sewer seperation. Remaining 22 CSO reconstructed and metered. WWTP expansion/upgrade completed.
PA0043885 | POTTSVILLE MAIN STP | Active | Major | Major Sewage Facility with CSO | Schuylkill | NERO | Pottsville City | 2008-12-15 | 2009-01-01 | 2013-12-31 | GREATER POTTSVILLE AREA SEW AUTH SCHUYLKILL CNTY | 401 N CENTRE ST, POTTSVILLE, PA 17901-1745 | 22 | 2000-03-09 | 2009-11-30 |  | TBD |  | Presumption | COA | AMD affected stream. NPDES renewal issued on 6/13/2012, effective 7/1/2012, requires updated LTCP to be submitted within one year of effective date. Updated LTCP received 6/12/2013.
PA0070041 | MAHANOY CITY MUN SEW AUTH | Active | Major | Major Sewage Facility with CSO | Schuylkill | NERO | Mahanoy City Boro | 2012-06-13 | 2012-07-01 | 2017-06-30 | MAHANOY CITY SEW AUTH SCHUYLKILL CNTY | 130 EAST CENTRE STREET, MAHANOY CITY, PA 17948-0215 | 1 | 2000-10-13 | 2002-09-09 | 2004-09-17 | TBD |  | No LTCP Approach |  | AMD affected stream. NPDES renewal issued 10/6/2017 requires submittal of updated LTCP within one year of effective date. In 2015 there were 78 recorded events; 13 of them were below 85% treatment; 4 of them were below 70% treatment. A presumptive approach 3 month storm plan needs to be developed. By capturing the 3-month design storm, a plan such as EPA’s LTCP-EZ for small communities or equivalent aims to reduce CSOs to no more than four overflows, on average, per year.
PA0070386 | SHENANDOAH MUN SEW AUTH | Active | Major | Major Sewage Facility with CSO | Schuylkill | NERO | Shenandoah Boro | 2017-10-06 | 2017-11-01 | 2022-10-31 | SHENANDOAH MUNI SEW AUTH SCHUYLKILL CNTY | 15 W WASHINGTON ST, SHENANDOAH, PA 17976-1708 | 14 | 1995-03-27 | 2004-04-30 | 2004-08-03 | TBD |  | Presumption (85% capture) |  | Part of DEP COA with ALCOSAN municipalities. Expected revision in LTCP submission to coincide with ALCOSAN planning effort. Permit issuance pending.
PA0217611 | PGH CITY COMBINED SEW OVERFLOWS | Active | Minor | Minor Sewage Facility with CSO | Allegheny | SWRO | Pittsburgh City | 2004-04-22 | 2004-05-01 | 2009-04-30 | PGH CITY ALLEGHENY CNTY | 1200 PENN AVE, PITTSBURGH, PA 15222 | 194 | 2000-05-17 | 2013-07-31 |  | TBD |  | Presumption | EPA/DEP COA Pending | NOI application issued as an Individual permit providing for an accelerated submission schedule. Failed to reply to DEP's additional information request to complete the application.
PA0254606 | SALTSBURG STP | Active | Minor | Minor Sewage Facility with CSO | Indiana | NWRO | Saltsburg Boro | 2022-07-12 | 2022-08-01 | 2027-07-31 | SALTSBURG BORO INDIANA CNTY | 320 POINT ST, SALTSBURG, PA 15681-1118 | 4 | 2000-10-06 | 2013-01-01 | 2013-05-02 | 2015-12-31 | PCCMP due 8/1/2023 | Presumption (85% capture) |  | The Clairton MA is going to apply for a permit for the additional outfalls. This is to be completed in addition to a COA. Waiting on legal review to issue COA and permit. Since the system was sold to Clairton Municipal Authority. COA now needs to include the Authority. This permit has not been issued yet verify date 12/9/2016
PAG062201 | EASTON CITY CSOS AND PUMP STATIONS | Active | Minor | PAG-06 CSOs | Northampton | NERO | Easton City | 2008-12-02 | 2009-01-01 | 2027-10-16 | EASTON CITY NORTHAMPTON CNTY | 123 S 3RD ST, EASTON, PA 18042-4503 | 2 | 2000-11-01 | 2002-09-09 | 2005-01-11 | TBD |  | No LTCP Approach |  | No Comments.
PAG062202 | LACKAWANNA RIVER BASIN SEW AUTH MOOSIC CSO | Active | Minor | PAG-06 CSOs | Lackawanna | NERO | Moosic Boro | 2013-12-05 | 2014-01-01 | 2027-10-16 | LACKAWANNA RIVER BASIN SEW AUTH | PO BOX 280, OLYPHANT, PA 18447-0280 | 3 | 1999-07-01 | 2000-07-27 | 2000-08-21 | TBD |  | No LTCP Approach |  | Moosic Pump Station No. 1 upgrade completed June 2000. New CSO structure including flow regulator, screening, overflow measurement, data logging & piping improvements completed March 2009.
PAG063501 | STEELTON BORO SANITARY SEWERS | Active | Minor | PAG-06 CSOs | Dauphin | SCRO | Steelton Boro | 2011-12-13 | 2012-01-01 | 2027-10-16 | STEELTON BORO AUTH DAUPHIN CNTY | 123 N FRONT ST, STEELTON, PA 17113 | 2 | 2005-10-14 | 2008-05-15 | 2008-09-03 | 2012-06-01 |  | Separation | COA | Steelton attempting to separate combined system. Held CSO GP as a result.
PAG066101 | PITCAIRN BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Pitcairn Boro | 2019-05-31 | 2019-05-31 | 2027-10-16 | PITCAIRN BORO ALLEGHENY CNTY | 582 6TH ST, PITCAIRN, PA 15140-1200 | 1 | 1997-11-17 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements, part of ALCOSAN system. Permit issuance pending.
PAG066102 | BRADDOCK BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Braddock Boro | 2019-05-06 | 2019-05-06 | 2027-10-16 | BRADDOCK BORO ALLEGHENY CNTY | 415 6TH ST, BRADDOCK, PA 15104-1635 | 9 | 2001-03-31 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | LTCP not approved. Under COA requirements. Part of ALCOSAN system.
PAG066103 | HOMESTEAD BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Homestead Boro | 2019-05-22 | 2019-05-22 | 2027-10-16 | HOMESTEAD BORO ALLEGHENY CNTY | 221 E 7TH AVE, HOMESTEAD, PA 15120-1511 | 1 | 1997-11-17 | 2003-04-11 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | LTCP not approved. Under ALCOSAN COA requirements.
PAG066104 | WILMERDING BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Wilmerding Boro | 2019-05-22 | 2019-05-22 | 2027-10-16 | WILMERDING BORO ALLEGHENY CNTY | 301 STATION ST, WILMERDING, PA 15148-1245 | 7 | 2001-04-03 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements for ALCOSAN system.
PAG066105 | RANKIN BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Rankin Boro | 2019-05-23 | 2011-09-01 | 2027-10-16 | RANKIN BORO ALLEGHENY CNTY | 320 HAWKINS AVE, BRADDOCK, PA 15104-2119 | 2 | 2013-07-31 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements part of ALCOSAN system.
PAG066106 | GIRTYS RUN SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Millvale Boro | 2019-05-31 | 2019-05-31 | 2027-10-16 | GIRTYS RUN JT SEW AUTH | 2236 BABCOCK BLVD, PITTSBURGH, PA 15237-3218 | 9 | 1996-02-09 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Permittee followiing ALCOSAN COA requirements however OCC must still process this agreement. Pemit issuance pending COA issuance.
PAG066107 | STOWE TWP SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Stowe Twp | 2013-06-18 | 2013-06-18 | 2027-10-16 | STOWE TWP ALLEGHENY CNTY | PO BOX 414, 555 BROADWAY AVE, MCKEES ROCKS, PA 15136 | 7 | 2005-12-02 | 2001-04-24 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements for ALCOSAN System. Developing a LTCP per a COA obligation in conjunction with ALCOSAN.
PAG066108 | WILKINS TOWNSHIP | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Wilkins Twp | 2017-08-29 | 2017-08-29 | 2027-10-16 | WILKINS TWP ALLEGHENY CNTY | 110 PEFFER RD, TURTLE CREEK, PA 15145-1148 | 2 | 2006-05-09 | 2013-07-30 | 2017-08-28 | 2018-12-31 | LTCP Completed, PCCMP approval and implementation pending. | Presumption | COA | Under COA requirements for ALCOSAN system. Permit reissuance pending.
PAG066109 | MCDONALD SEW SYS | Active | Minor | PAG-06 CSOs | Washington | SWRO | McDonald Boro | 2019-05-31 | 2019-05-31 | 2027-10-16 | MCDONALD SEW AUTH | 151 SCHOOL ST, MCDONALD, PA 15057 | 20 | 1999-01-19 | 2013-07-31 |  | 2026-12-23 | LTCP Completed, PCCMP approval and implementation pending. | Presumption | DEP Enforcement Action | Part II permit under review for complete system separation. Pennvest separation project applications received.
PAG066110 | CRAFTON BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Crafton Boro | 2019-03-05 | 2019-03-05 | 2027-10-16 | CRAFTON BORO ALLEGHENY CNTY | 100 STOTZ AVE, PITTSBURGH, PA 15205 | 3 | 2000-11-17 | 2001-03-26 | 2018-01-08 | 2022-08-01 | Feasibility Study Submission | Presumption | COA | LTCP not approved. Under COA requirements LTCP must be revised. Part of ALCOSAN System.
PAG066112 | MCKEES ROCKS BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | McKees Rocks Boro | 2019-05-15 | 2019-05-15 | 2027-10-16 | MCKEES ROCKS BORO ALLEGHENY CNTY | 340 BELL AVE, MC KEES ROCKS, PA 15136-3514 | 3 | 1999-08-25 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements for ALCOSAN system.
PAG066113 | ASPINWALL BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Aspinwall Boro | 2019-05-01 | 2019-05-01 | 2027-10-16 | ASPINWALL BORO ALLEGHENY CNTY | 217 COMMERCIAL AVE, ASPINWALL, PA 15215-3024 | 4 | 1995-03-04 | 2002-12-30 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | LTCP not approved. Under COA requirements. Part of ALCOSAN System.
PAG066114 | N BRADDOCK BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | North Braddock Boro | 2019-05-31 | 2019-05-31 | 2027-10-16 | NORTH BRADDOCK BORO ALLEGHENY CNTY | 600 ANDERSON ST, NORTH BRADDOCK, PA 15104 | 1 | 2001-04-02 | 2003-03-28 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | LTCP not approved. Under COA requirements. Part of ALCOSAN system. Permit issuance pending.
PAG066116 | W VIEW BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | West View Boro | 2019-05-10 | 2019-05-10 | 2027-10-16 | WEST VIEW BORO MUNI AUTH ALLEGHENY CNTY | 441 PERRY HWY, PITTSBURGH, PA 15229-1818 | 2 | 2002-12-12 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | 9/3/02 LTCP not approved. Under COA requirements for ALCOSAN system.
PAG066118 | TURTLE CREEK BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Turtle Creek Boro | 2019-05-28 | 2019-05-28 | 2027-10-16 | TURTLE CREEK BORO ALLEGHENY CNTY | 125 MONROEVILLE AVE, TURTLE CREEK, PA 15145-1862 | 7 | 2005-12-01 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements for ALCOSAN system. Permit issuance pending.
PAG066120 | E PGH BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | East Pittsburgh Boro | 2019-05-20 | 2019-05-20 | 2027-10-16 | EAST PGH BORO ALLEGHENY CNTY | 813 E PITTSBURGH MALL, EAST PITTSBURGH, PA 15112-1207 | 3 | 1997-11-17 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements in ALCOSAN System.
PAG066121 | ARNOLD CITY SEW SYS | Active | Minor | PAG-06 CSOs | Westmoreland | SWRO | Arnold City | 2018-09-19 | 2018-09-19 | 2027-10-16 | ARNOLD CITY WESTMORELAND CNTY | 1829 5TH AVE., ARNOLD, PA 15068 | 2 | 2010-02-09 | 2013-07-31 | 2016-12-02 | 2021-12-31 |  | Presumption | EPA Enforcement Action | Under EPA Enforcement Action for the MSA of the City of New Kensington System. Individual permit issuance pending.
PAG066123 | W HOMESTEAD SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | West Homestead Boro | 2019-05-16 | 2019-05-16 | 2027-10-16 | WEST HOMESTEAD BORO ALLEGHENY CNTY | 456 W 8TH AVE, WEST HOMESTEAD, PA 15120-1030 | 4 | 2013-07-31 | 2013-07-31 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements for ALCOSAN system. Permit reissuance pending.
PAG066125 | SHARPSBURG BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Sharpsburg Boro | 2019-05-30 | 2019-05-30 | 2027-10-16 | SHARPSBURG BORO ALLEGHENY CNTY | 1611 MAIN ST, PITTSBURGH, PA 15215-2609 | 6 | 1996-12-04 | 2004-01-13 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements for ALCOSAN system.
PAG066126 | CARNEGIE BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Carnegie Boro | 2019-05-28 | 2019-05-28 | 2027-10-16 | CARNEGIE BORO ALLEGHENY CNTY | ONE VETERANS WAY, CARNEGIE, PA 15106 | 11 | 2005-12-02 | 2013-07-30 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | Under COA requirements. Part of ALCOSAN system.
PAG066128 | SWISSVALE BORO SEW SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Swissvale Boro | 2019-05-28 | 2019-05-28 | 2027-10-16 | SWISSVALE BORO ALLEGHENY CNTY | 7560 ROSLYN ST, PITTSBURGH, PA 15218-2556 | 1 | 1997-01-23 | 2003-02-03 |  | 2026-01-01 | Feasibility Study Submission | Presumption | COA | COA development as part of ALCOSAN system pending needed action by OCC. Under the anticipated COA requirements their LTCP shall be due 7/30/2013.
PAG066130 | EXPORT BORO SEW | Active | Minor | PAG-06 CSOs | Westmoreland | SWRO | Export Boro | 2019-03-05 | 2019-03-05 | 2027-10-16 | EXPORT BORO WESTMORELAND CNTY | 5944 JOHNSON AVE, EXPORT, PA 15632-1120 | 5 | 1999-03-04 | 2013-12-04 | 2018-10-01 | 2022-10-01 |  | Presumption |  | Watershed improvements and Rehabilitation of (2) regulator structures underway. LTCP submission to be required in pending Individual permit issuance/ COA possible.
PAG066133 | ROCHESTER BORO SEW SYS | Active | Minor | PAG-06 CSOs | Beaver | SWRO | Rochester Boro | 2013-10-03 | 2013-10-03 | 2027-10-16 | ROCHESTER BORO SEW & MAINT AUTH | PO BOX 563, ROCHESTER, PA 15074-0563 | 4 | 2008-09-30 | 2011-12-16 | 2013-03-22 | 2017-12-31 | Implementation Underway | Presumption | COA | COA for multi-municipal issued and amended to required certain LTCP submital date. LTCP receipt pending. Part II permit for system separation approved and PennVest funding application revd.
PAG066135 | CORAOPOLIS CSO COLL SYS | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Coraopolis Boro | 2019-05-29 | 2019-05-29 | 2027-10-16 | CORAOPOLIS WATER & SEW AUTH ALLEGHENY CNTY | 1012 5TH AVE, CORAOPOLIS, PA 15108-1804 | 6 | 2000-12-01 | 2008-01-03 |  | TBD | Under Review | Presumption |  | Individual permit authorization likely to include defined LTCP implementation schedule. Individual permit PA0026352 now assigned to the Riverview MSA.Revised LTCP received on 3/2008. CMSA wants to amend LTCP to include flow monitoring and 537 planning.Permit Issuance pending.
PAG066139 | INGRAM BORO CSO C 19 DISCH | Active | Minor | PAG-06 CSOs | Allegheny | SWRO | Ingram Boro | 2017-09-06 | 2017-09-06 | 2027-10-16 | INGRAM BORO ALLEGHENY CNTY | 40 W PROSPECT AVE, PITTSBURGH, PA 15205 | 1 | 1999-04-27 | 2013-07-31 | 2017-07-21 | 2020-10-20 | Feasibility Study Submission | Presumption |  | This has been issued to replace old permit # PA0253740
PAG066140 | ETNA BORO CSO SEW SYS | Active | Minor | Minor Sewage Facility with CSO | Allegheny | SWRO | Etna Boro | 2019-05-31 | 2019-05-31 | 2027-10-16 | ETNA BORO ALLEGHENY CNTY | 437 BUTLER ST, ETNA, PA 15223-2126 | 9 | 1999-04-27 | 2013-07-31 |  | 2026-01-01 | Feasibility Study and GI Proposals | Presumption | COA | A CSO-related bypass has been constructed at the WWTP. 3/28/12 update: The CSO-related bypass was formally approved as part of the LTCP, thereby deeming it a "permanent" structure. DEP is not requiring further action from Kane-Pine St at this point. This plant now has an approved CSO-related bypass, with disinfection of all flows reaching the STP.
PAG066141 | MUNHALL BORO CSO SEW SYS | Active | Minor | Minor Sewage Facility with CSO | Allegheny | SWRO | Munhall Boro | 2019-05-22 | 2019-05-22 | 2027-10-16 | MUNHALL SANI SEW MUNI AUTH | 1809 WEST ST, MUNHALL, PA 15120-2532 | 4 | 2002-12-02 | 2002-11-04 |  | 2026-01-01 | Feasibility Study Submission | Separation | COA
1 | Unless otherwise indicated in this spreadsheet, permits with past expiration dates have been administratively extended.
2 | Dates reflect the most recent submissions and are based on the best available information at the time the information was collected but are not guaranteed to be accurate.
Note on N74: Kumar: Earlier was 39 outfalls but Regional staff may have corrected it to 37 CSO outfalls in eFACTS

## Former CSOs
Permit No. | Facility Name | Status | Major or Minor | County | Region | Facility Address | Permit Issuance Date | Permit Expiration Date | LTCP Received Date | LTCP Approved Date | LTCP Completion Date | NMC Received Date | Comments/Status
PA0020940 | TUNKHANNOCK BORO MUN AUTH | Active | Minor | Wyoming | NERO | 203 W TIOGA ST, TUNKHANNOCK, PA 18657-6655 | 2013-08-09 | 2018-08-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in May 2010.
PA0021539 | WILLIAMSBURG STP | Active | Minor | Blair | SCRO | 305 E 2ND ST, WILLIAMSBURG, PA 16693-1041 | 2011-03-24 | 2016-03-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in September 2007.
PA0022241 | CALIFORNIA BORO STP | Active | Major | Washington | SWRO | 225 3RD ST, CALIFORNIA, PA 15419-1131 | 2013-06-19 | 2018-06-30 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility.
PA0022306 | SHADY AVE STP | Active | Minor | Fayette | SWRO | PO BOX 330, BROWNSVILLE, PA 15417 | 2009-08-24 | 2014-08-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in March 2011.
PA0022331 | W ELIZABETH STP | Active | Major | Allegheny | SWRO | 125 LOWER FIRST ST, WEST ELIZABETH, PA 15088 | 2014-10-21 | 2019-10-31 | 2006-02-15 | 2006-06-12 | 2011-01-20 | 2006-01-17 | Former CSO facility. Removed from CSO list in October 2014.
PA0024163 | REVLOC STP | Active | Minor | Cambria | SWRO | PO BOX 247, REVLOC, PA 15948-247 | 2014-06-18 | 2019-06-30 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in March 2011.
PA0024341 | CANTON BORO AUTH SEW SYS & STP | Active | Minor | Bradford | NCRO | PO BOX 237, CANTON, PA 17724 | 2014-12-08 | 2019-12-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in June 2005.
PA0024406 | MT CARMEL MUNI SEW COLL SYS & STP | Active | Major | Northumberland | NCRO | 137 W 4TH ST STE 4, MOUNT CARMEL, PA 17851 | 2013-09-18 | 2014-01-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in October 2013.
PA0024481 | MEYERSDALE STP | Active | Minor | Somerset | SWRO | 215 MAIN ST RM# 2B, MEYERSDALE, PA 15552 | 2002-08-08 | 2007-08-08 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in November 2013.
PA0024511 | REDBANK VALLEY STP | Active | Minor | Clarion | NWRO | 243 BROAD ST, NEW BETHLEHEM, PA 16242-1001 | 2010-05-18 | 2015-05-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in September 2005.
PA0024686 | MID MON VLY WPCA STP | Active | Minor | Washington | SWRO | PO BOX 197, ALLENPORT, PA 15412-197 | 2011-11-10 | 2016-11-30 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in March 2011.
PA0025810 | SHADE CTL CITY JT AUTH STP | Active | Minor | Somerset | SWRO | 429 SUNSHINE AVE, CENTRAL CITY, PA 15926 | 2014-10-31 | 2019-10-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility.
PA0026832 | ELLWOOD CITY WWTP | Active | Major | Lawrence | NWRO | 525 LAWRENCE AVE, ELLWOOD CITY, PA 16117-1927 | 2010-09-17 | 2015-09-30 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in June 2009.
PA0027219 | UNIONTOWN STP | Active | Major | Fayette | SWRO | 90 ROMEO LN, UNIONTOWN, PA 15401 | 2014-09-08 | 2019-09-30 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in March 2011.
PA0027570 | BRUSH CREEK STP | Active | Major | Westmoreland | SWRO | 12441 ROUTE 993, N HUNTINGDON, PA 15642-0366 | 2011-11-17 | 2016-11-30 | 2007-10-29 | 2010-03-04 | 2018-01-01 | 2003-05-07 | Former CSO facility. Removed from CSO list in December 2016.
PA0037711 | EVERETT STP | Active | Minor | Bedford | SCRO | 100 MECHANIC ST, EVERETT, PA 15537-1177 | 2012-11-28 | 2017-11-30 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in September 2011.
PA0037818 | SALTSBURG BORO STP | Inactive | Minor | Indiana | SWRO | 320 POINT ST, SALTSBURG, PA 15681-0104 | 2004-08-17 | 2009-08-31 | 2001-10-15 | 2013-05-02 | 2015-12-31 | 2000-10-06 | Former CSO facility. Removed from CSO list on November 19, 2015.
PA0037966 | MOSHANNON VALLEY JT SEW AUTH - STP | Active | Major | Centre | NCRO | 829 NORTH 9TH ST, PHILIPSBURG, PA 16866 | 2012-11-28 | 2015-12-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in March 2000.
PA0038164 | CONFLUENCE BORO STP | Active | Minor | Somerset | SWRO | PO BOX 6, CONFLUENCE, PA 15424 | 2008-07-08 | 2013-07-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility.
PA0038920 | BURNHAM STP | Active | Minor | Mifflin | SCRO | 200 1ST AVE, BURNHAM, PA 17009-1640 | 2011-10-24 | 2016-01-31 | 2001-10-29 | 2003-03-05 |  | 2000-11-06 | Former CSO facility. Removed from CSO list in July 2013.
PA0039489 | GARRETT BORO STP | Active | Minor | Somerset | SWRO | 307 MUNI RD, GARRETT, PA 15542 | 2014-04-29 | 2019-04-30 | 2006-04-14 | 2008-03-31 | 2010-01-01 | 2005-05-04 | Former CSO facility. Removed from CSO list November 2013.
PA0042234 | KITTANNING BORO STP | Active | Major | Armstrong | SWRO | PO BOX 993, KITTANNING, PA 16201-0993 | 2009-03-17 | 2014-03-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO Facility. Removed from CSO list in November 2013.
PA0046159 | HOUTZDALE MUN SEW | Active | Minor | Clearfield | NCRO | P.O. BOX 277, HOUTZDALE, PA 16651-0277 | 2012-03-10 | 2017-03-31 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in May 2001.
PA0092355 | BELLE VERNON STP | Active | Minor | Fayette | SWRO | PO BOX 181, BELLE VERNON, PA 15012-0181 | 2009-10-09 | 2014-10-31 | 2004-04-05 |  |  | 2001-02-09 | Former CSO facility. Removed from CSO list in November 2013.
PA0096229 | MARIANNA W BETHLEHEM STP | Active | Minor | Washington | SWRO | P.O. BOX 428, MARIANNA, PA 15345-0428 | 2010-06-22 | 2015-06-30 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility.
PA0253693 | E CONEMAUGH BORO SEW SYS | Inactive | Minor | Cambria | SWRO | 355 FIRST ST, CONEMAUGH, PA 15909 | 2008-11-04 | 2013-11-30 | 2011-12-01 | 2007-09-04 | 2007-11-05 | 2007-09-04 | Former CSO facility. Removed from CSO list on November 30, 2016.
PA0253901 | DALE BORO CSO SEW SYS | Inactive | Minor | Cambria | SWRO | 810 BEDFORD ST, JOHNSTOWN, PA 15902 | 2009-11-04 | 2014-09-30 | 2001-11-07 | 2008-05-28 | 2008-07-10 | 2012-12-01 | Former CSO facility. Removed from CSO list on November 21, 2016.
PA0253936 | FERNDALE BORO SEW SYS | Inactive | Minor | Cambria | SWRO | 109 STATION ST, JOHNSTOWN, PA 15905 | 2009-09-17 | 2014-03-31 | 2008-08-05 | 2008-08-20 | 2012-10-01 | 2001-10-02 | Former CSO facility. Removed from CSO list on March 31, 2016.
PAG066129 | MAYVIEW STATE HOSP SEW SYS | Inactive | Minor | Allegheny | SWRO | 1601 MAYVIEW RD, BRIDGEVILLE, PA 15017 | 1997-02-03 | 2002-02-02 | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility. Removed from CSO list in August 2011.
PAG066131 | FREEDOM BORO CSO | Inactive | Minor | Beaver | SWRO | PO BOX 201, FREEDOM, PA 15042-1738 | 2010-06-25 |  | 2014-03-12 |  |  | 2014-03-12 | Former CSO facility.
PAG066132 | E ROCHESTER BORO CSO | Inactive | Minor | Beaver | SWRO | 760 SPRUCE AVE, EAST ROCHESTER, PA 15074 | [6 empty] | Former CSO facility. Permit Terminated 8/13/2020.
PA0023175 | KINZUA ROAD STP KANE | Active | Major
PA0021571 | MARYSVILLE STP | Active | Minor | Perry | SCRO | 200 OVERCREST RD, MARYSVILLE, PA 17053-1159 | 2012-02-23 | 2017-02-28 | 1996-09-24 | 1996-09-24 | 2017-07-17 | 1996-09-24 | Former CSO Facility. Final separation completed 7/17/2018.
PA0023248 | BERWICK MUN AUTH | Active | Major | Columbia | NCRO | 1108 FREAS AVE, BERWICK, PA 18603-1710 | 2016-09-16 |  | 2010-10-15 | 2010-10-28 | 2019-06-01 | 2000-05-15 | Former CSO Facility. Final separation completed 4/9/2019. | 2010-10-26 | 2020-12-31 | Separation completed 4/9/19 | Separation
PA0028673 | GALLITIZIN BORO - WWTP | Active | Minor | Cambria | SWRO | 411 CONVENT ST STE 10, DEGOL PLAZA, GALLITZIN, PA 16641-1244 | 2020-08-06 | 2025-08-31 | 2008-06-30 | 2014-08-21 | 2017-03-31 | 2002-12-03 | Former CSO facility; final separation completed 3/31/2017
PA0252751 | LEET TWP MUN AUTH - SEW COLL SYS | Active | Minor | Allegheny | SWRO | 198 AMBRIDGE AVE, AMBRIDGE, PA 15003-1278 | 2010-03-24 | 2015-03-31 | 2013-12-04 |  | Completed | 2010-04-01 | Separated and closed CSO Outfall. Permit rescinded 6/12/18.
PA0254690 | PORT VUE BOROUGH | Inactive | Minor | Allegheny | SWRO | [7 empty] | Port Vue Borough's CSO responsibilities have been incorporated into the NPDES Permit for McKeesport WPCP (PA0026913) as of January 24, 2018.