## Table 14-1 JPA Printout
County | Municipality | Date Initial Letter Sent | Initial Delivery Confirmation | Follow-up Letter Sent | Follow-up Delivery Confirmation | Response Received | Stormwater Plan Consistent | Floodplain Consistent
Allegheny | Elizabeth | 2015-12-22 | 2015-12-23 | N/A | N/A | 2016-01-06 | Y | Y
| Forward | 2015-12-22 | 2015-12-28 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
Cambria | Cambria | 2015-12-22 | 2015-12-28 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Cresson | 2015-12-22 | 2015-12-23 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Jackson | 2015-12-22 | 2015-12-23 | N/A | N/A | 2015-12-29 | Y | Y
| Munster | 2015-12-22 | 2015-01-06 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Washington | 2015-12-22 | 2015-12-23 | 2016-02-08 | 2016-02-09 | 2016-02-10 | Y | Y
Indiana | Burrell | 2015-12-22 | 2015-12-24 | 2016-02-08 | 2016-02-11 | Pending | TBD | TBD
| East Wheatfield | 2015-12-22 | 2015-12-29 | N/A | N/A | 2016-01-05 | NO PLAN | NO PLAN
| West Wheatfield | 2015-12-22 | 2015-12-23 | N/A | N/A | 2016-01-11 | Y | N/A
Washington | Chartiers | 2015-12-22 | 2015-12-23 | 2016-03-22 | N/A | 1/29/2016 More information requested | TBD | TBD
| North Strabane | 2015-12-22 | 2015-12-23 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Nottingham | 2015-12-22 | 2015-12-23 | N/A | N/A | 2016-01-12 | Y | Y
| Union | 2015-12-22 | 2015-12-23 | 2016-02-08 | 2016-02-09 | 2016-02-17 | Y | Y
Westmoreland | Derry | 2016-01-15 | 2016-01-19 | 2016-02-18 | 2016-02-19 | Pending | TBD | TBD
| Hempfield | 2015-12-22 | 2015-12-23 | N/A | N/A | 1/8/2016 More information requested | TBD | TBD
| Jeannette | 2015-12-22 | 2015-12-23 | 2016-02-09 | 2016-02-10 | 2/10/16 More information requested | TBD | TBD
| Loyalhanna | 2015-12-22 | 2015-12-23 | N/A | N/A | 2015-12-28 | Y | Y
| Murrysville | 2015-12-22 | 2015-12-23 | N/A | N/A | 2016-01-08 | Y | Y
| Penn | 2015-12-22 | 2015-12-23 | 2016-02-08 | 2016-02-09 | 2016-02-11 | Y | Y
| Rostraver | 2015-12-22 | 2015-12-23 | N/A | N/A | 1/5/2016 Request for Zoning Board application | Y | TBD
| Salem | 2015-12-22 | 2015-12-28 | N/A | N/A | None Required | N/A | N/A
| Sewickley | 2015-12-22 | 2015-12-23 | N/A | N/A | 2/17/2016 More information requested | TBD | TBD
| South Huntingdon | 2015-12-22 | 2015-12-28 | N/A | N/A | 2016-01-04 | Y | Y
Formulas:
Date Initial Letter Sent = '[1]ALL SW COUNTIES'!H3
Initial Delivery Confirmation = '[1]ALL SW COUNTIES'!I3
Response Received = '[1]ALL SW COUNTIES'!J3
Follow-up Letter Sent = '[1]ALL SW COUNTIES'!M4