## Funding and Multi-Grant Coord.
Final Recommendation: Funding and Multi-Grant Coordination Progress Team Strategies for Success
The ISSUE(s) were identified at the Clean Water Gathering - Progress Teams identified 15 PRIORITIES to be taken to address the issues - Priority Action Members developed a strategy to successfully accomplish the priority action item ie. Strategies for Success
Funding and Multi-Grant Coordination Progress Team members:
Numbering (corresponds to a tracking matrix) | Progress Team Priority Action Members | Scope of the Priority Action Item | How should action be taken? What are the steps needed for action? How could the action steps be funded? | Who is required to take action? Who has the authority to support the action? What agencies need to be involved? Who can move this forward? Who can get this unstuck? | When should action be taken? What is the priority level? Is this something that is a near-term/long-term project? Can this be addressed immediately? | Unknowns that will need to be addressed | Additional Comments
Priority Action Item: Create a centralized funding tool
| Josh Clark, Stacie Chornak, Devin Gray, Miranda McCleaf, Matt Royer | To provide a funding decision support tool/concierge (publicly accessible) by developing an electronic system incorporating a simple series of questions regarding project details that integrates AI to provide an informed output on potential funding sources with GIS layer-like visualization for geographic considerations. | • Arrange periodic communication with the CODE Team as they roll out their Phase 1 searchable grants tool and their Phase 2 common application at the state level. Advocate for incorporation of GIS-layer component due to importance of location-specific funding sources. Advocate for an early alert feature as grants are close to opening and display when grant was last updated and eligibility. Before suggesting a pilot for a county-specific (Franklin or Cumberland Co.) grant search tool, would want to see outputs/tool from CODE. • Determine protocol for updating grant information in a timely way (currently envisioned to be a SharePoint-style system, decentralized updates at the program office posted to a centralized sharing system). • Determine if federal funding information can be included in CODE's work eventually. In the interim, direct partners to Chesapeake Conservancy's Federal Funding Navigator (note: Chesapeake Conservancy may need resources to publish online as a packaged user interface - currently a filterable spreadsheet). Commentary on administrative burden, relative difficulty may inhibit sharing with DEP, DCED partners in its current form. | • Members of the CODE Team (contact could be Dan Rosenberg or other identified team member). • Members of Chesapeake Conservancy (contact could be Ben Alexandro or other identified staff member). • DEP, DCNR, and DCED staff with specific input/insights into searchable tool/common application as well as conservation partners willing to test the tools. If pursuing pilot in long-term, Franklin and/or Cumberland County partners. | Phase 1 - CODE's searchable PA grants tool is near-term with potential delivery as early as Q4 2024. Phase 2 - CODE's common application overhaul (paired with searchable tool) potentially online in 2026. Chesapeake Conservancy's Federal Funding Navigator currently assembled but not packaged as a user interface. | Can CODE accommodate early alert system, incorporate GIS capabilities? Can CODE include federal funding sources? | The work done by CODE ties the searchable tool (at the state level) to the common application system (another small group area of focus).
F1a
Priority Action Item: Common application/LOI concept
| Teah Gray, Carly Dean, Marel King, Natahnee Miller, Lane Whigham | Simplify the application process by providing tools/information upfront, accessing multiple funding sources in one system, and providing storage places for invoices/reports over the life of a funding award through a common funding portal. | • Arrange periodic communication with CODE in the midst of their Phase 2 common application portal overhaul, which is planned to include features to guide grant management from the initial application through the reporting and end of the grant lifecycle. The Office of Administration is leading this effort. | • Members of the CODE Team (contact could be Dan Rosenberg or other identified team member). • DEP, DCNR, and DCED staff with specific input/insights into common application portal as well as conservation partners willing to test the tools (i.e., Teah Gray, Carly Dean). • DEP staff already in communication with CODE include Sam Harmon and Michelle Devaney. DCNR staff from the Bureau of Recreation and Conservation (BRC), Shane Hoover, also working with CODE. | The Phase 2 common application portal expected for delivery in 2026 by CODE. |  | This may overlap with reducing administrative burden in the Staff Retention and Training Progress Team. If there was less administrative burden that could reduce costs in other areas.
F2a
|  | Reduce applicant time spent answering similar questions (but different enough requiring significant time input) by creating a common set of core application questions. | • Through the communication and process structures set up by CODE as they engage state agencies in development of the common portal system, work to develop a streamlined set of application questions common among conservation agencies. | Specific contacts from funders that sign off on using core questions. Note: Chesapeake Conservancy reviewed applications from the following funding programs that might be a good fit for this: PA DEP Growing Greener and CAP, PA DCNR Forest Buffer, NFWF INSR and SWG. EPA should also be contacted regarding 319 programs. | • A draft common set of application questions has already been developed by the Chesapeake Conservancy and been reviewed by several other applicants but completion of CODE's Phase 2 common application portal not expected until 2026. • Funders would need to review the common set of questions annually to keep this updated/relevant. | NFWF is aware of the effort to streamline a common set of application questions and seems interested in participating in that. How can federal partners be engaged? Additionally, how can this recommendation complement what's already being done with CODE to detail valuable next steps in this area? | This could overlap with the funding network concept in the "Connecting Projects with Funding" small group. Funder network could be used to vet application questions.
F2b
Priority Action Item: Connecting projects and funding
| Natahnee Miller, Mary Matscavage, Miranda McCleaf, Stephen Schelander | Create a consistent knowledge base across state agencies and local/regional partners for funding opportunities by coordinating two simultaneously operational networks understood as the "Funding Network" and the "Partner Network." | • Fund a coordinator staff position facilitating meetings and keeping communication lines open between "Funder Network" and "Partner Network". • Utilize existing funding agency relationships to build the network. For example, DCED sends Watershed Restoration Program grants to DEP for review and Greenways Program grants over to DCNR and DEP interacts with PENNVEST in its Pay for Performance Program. Additionally, the Tri-Secretaries meeting ties together PDA, DEP, and DCNR. • Set up structure for how communication will occur in Funding Network and protocol for reviewing high-impact water quality projects and for them to receive Partner Network feedback on difficulty or ways to change funding program. • Use existing CDFR structure and meetings with Conservation Districts to identify who should be included in the Partner Network (agenda item for future roundtables discussing who should be included) • Engage Office of Environmental Justice regional staff to include disadvantaged communities, DCED Regional Directors to engage municipalities, and Governor's Commissions for statewide exposure. | • A coordinator. • Existing connections: Individuals that connect funding agencies include the following: Cynthia Dunlap (Greenways DCNR reviewer), Shane Kleiner (Watershed Restoration DEP reviewer), Richard Wright (PENNVEST contact at DEP for the State Revolving Fund), Jill Whitcomb and Ashley Hullinger (PENNVEST contact at DEP for Pay for Performance), Doug Wolfgang and MIke Roth (PENNVEST contact at SCC for Pay for Performance), DCED, DEP, DCNR, SCC, PENNVEST, and PDA staff. • A partner network using Conservation District Field Reps (CDFRs), regional reps from Office of Env. Justice, regional directors from DCED, DCED Deputy Secretary, Center for Local Government, potential to expand further with Governor's Commissions, Office of Administration (monthly speaker series), Office of Health Equity, CODE, etc. | • Near Term - Create a "coordinator" position to work with the "Funding Network" and "Partner Network" • Funding Network would meet quarterly to review high-impact projects in need of funding • Partner Network could be developed through existing structures but would need coordination to organize messaging and present projects to funder network. | • What agency or what entity would house the "coordinator"? | Ideally the Partner Network would have access to a project prioritization list that cuts across counties (regionwide) so that high-impact water quality projects can be highlighted regionally and brought to the funding network for discussion on funding solutions. Additionally, this network could be used for outreach.
F3a
Priority Action Item: Leveraging funding
F4a | Megan Blackmon, Rob Boos, Josh Clark, Carly Dean, Devin Gray, Matt Royer, Stephen Schelander, Lane Whigham | Provide upfront cash for matching capital at low interest through the PENNVEST link deposit program. | • PENNVEST recruits local banks who would make loans to conservation partners implementing approved BMPs. PENNVEST pays the difference in interest rates so that the conservation partner only deals with a low interest rate. The loan is standard for the conservation partner who interacts with a typical local bank. | PENNVEST, willing local bank partners, conservation partners (landowners or nonprofits). | Once a local bank partner is found, then Board approval can be secured for the program to begin. | Local bank needed for partnership to work. Unknown which financial entity would be willing. | Will need to rely on Outreach and Education strategies to make folks aware within specific geographic areas where this program is happening.
|  | Educate on MBE/WBE and BABA requirements or other requirements tied to mixing various funding sources. | • Develop a rubric/matrix for award compliance for subawardees and another for contractors that guide users into asking pertinent questions regarding funding streams and where to go to get resources/interpretation. • Store available resources for use at a public-facing site, emphasizing plain language resources. | Project partners to develop draft rubric/matrix (nonprofit entities like Lancaster Clean Water Partners or Chesapeake Conservancy or partners like HRG and PennBid). Entities like The Center (PSU), EPA, and PennBid to view and vet the matrix. Subawardees and subcontractors to use the tool to understand their roles with mixed funding streams and various layers. | Near term - Project partners have begun to develop a list of compliance issues that could provide structure to developing a matrix. PennBid also has frequently asked compliance questions that have come up. Once developed, rubric would be vetted by entities like The Center (PSU) and EPA and could also be circulated further for use. | Unknown which entity would be best for storing public-facing resources regarding funding requirements. Could tie in with Education and Outreach's proposal on a public-facing site. | Tech Assistance and Admin Progress Team's small group, "Engineering assistance is needed" may be reaching out to tech professionals, and this could be expanded to reaching out to subcontractors.
F4b
F4c |  | Address common decision points affecting funding choices among partners by surveying funding programs to see if increased flexibility is possible. | • Develop a list of common decision points affecting use of funding sources (i.e. BMP requirements, landowner resistance to direct govt. contracts, landowner agreement duration, maintenance requirements, prevailing wage, partner cash on hand, reporting requirements, location) • Survey funding program admin to see if any aspects of programs could be changed to accommodate these commonly identified issues. • Depending on outcome continue to work to change programs or develop training to address pressure points where funding programs cannot be flexible. | Project partners (to list common decision points); funding program admin staff to respond. | Could begin near term with development of a list of common decision points vetted by multiple project partners and then circulated. |  | This recommendation could work with a "Funding Network" generated as a result of the "Connecting projects and funding" small group.
Priority Action Item: Outreach and education
| Teah Gray, Stacie Chornak, Shane Kleiner, Devin Gray, Rachel Stahlman | Strengthen existing communication structures/tools to reach a wide audience across the state with consistent information using a public-facing website. | • Review RFP used to create Center for Water Quality Excellence (CWQE) and determine if DEP is capable of maintaining a public-facing site focused statewide rather than just on Lancaster and York. Use information already gathered on the Center for Water Quality Excellence as a reference point for the public and project partners, linking relevant content (including publicly accessible CWA resources) as needed. • Clear communication flowing from DEP Program Admin to various partner networks about the site and information contained within using CAP Coordinators to handle specific county inquiries or directing folks to correct sources. • Consistent communication about where resources are located through Friday emails, monthly newsletters, etc. | DEP Program Staff to review RFP (available from PENNVEST) and determine if resources could be made available for public-facing website (statewide water quality focus). If so, would need funding to maintain site and would need PENNVEST to release the data (PENNVEST would be willing). Communication networks to include CAP Coordinators, CDFRs and their facilitated round tables, regional Office of Env. Justice staff, regional directors at DCED, Governor's Commissions, Local Government Commission (PA General Assembly), PMAA (Pennsylvania Municipalities Authorities Association) | Could be near-term once a decision is made about available resources. Curent website is still accessible through December 2024. Note: Land Logic's funding to maintain the CWQE ends December 2024. A decision likely needed short-term about how to move ahead. Unclear what happens with the site beyond December 2024.
F5a
|  |  | Intentionally promote peer to peer knowledge sharing through more intentional use of Webinar Wednesdays or similar venue and through making intentional connections across counties (facilitated by Conservation District Field Reps) as needed to discuss project strategies and techniques. | CAP Coordinators, CDFRs, Conservation District Staff, DEP Program Admin, Conservation Partners | Near Term Possible (easily implementable)
F5b