## Staff Building-Retention
Final Recommendation: Staff Building and Retention Progress Team Strategies for Success
The ISSUE(s) were identified at the Clean Water Gathering - Progress Teams identified 15 PRIORITIES to be taken to address the issues - Priority Action Members developed a strategy to successfully accomplish the priority action item ie. Strategies for Success
Staff Building and Retention Progress Team members:
Numbering corresponding to SSM | Progress Team Priority Action Members | Scope of the Priority Action Item | How should action be taken? What are the steps needed for action? How could the action steps be funded? | Who is required to take action? Who has the authority to support the action? What agencies need to be involved? Who can move this forward? Who can get this unstuck? | When should action be taken? What is the priority level? Is this something that is a near-term/long-term project? Can this be addressed immediately? | Unknowns that will need to be addressed | Additional Comments
Priority Action Item: Make Management and Leadership Training Available
S1a | Teddi Stark, Kristen Wolf, Erin Letavic, and Willie Null | The public sector environmental industry suffers from a lack of management skills and effective leadership. Training is considered to be optional due to the urgency of daily work responsibilities. Training needs to be available, accessible, valued, and adapted to the current and future needs of conservation leaders. | Explore, organize, coordinate and expand (if needed) on the vast library of training resources across agencies and programs. Develop specific training plans, curriculum, and/or lesson plans for individuals looking to expand their knowledge on different and or specific subjects. New hire lesson plan, management training lesson plan, effective communication lesson plan, etc. Expand current training resources and making them accessible across state agencies as well as other county and local partners. Examples include but are not limited to • DCNR mentorship program • Internal state library of recorded trainings • CD Leadership Development Program • DEP Clean Water Academy In order to accomplish this task a scope of what training is already available, and if it is relevant and up to date is needed. Details like what organization is responsible for the training, where the training is located, how it can be accessed, and a summary of what the training included is needed. | PACD, SCC, DEP, DCNR, Office of Administration, etc. Tiered approach with each agency or program organizing their own resources. Then one organization taking one the larger admin task of coordinating across programs | Near -term project: begin immediately | Could AI be used for this gathering, organizing, and coordinating?
S1b |  |  | Retitle/update/expand the current PACDs Leadership.org survey and associated modules. Currently the modules provides high level information about conservation districts and their responsibilities. Update material for district managers and conservation district staff so that the survey can be taken on a yearly basis to assess the type of continuous education that is needed. Update and expand current modules to accommodate specific needs of different programs within a conservation district. Use the results of the survey to inform what new training modules are needed. https://www.paleadership.org/training_modules/ | PACD, Leadership Development Program Committee, SCC | Near -term project: begin immediately | Should one new survey be created? Or should there be multiple surveys depending on the staff person taking the survey
Priority Action Item: Diversify staff hires: Hire staff with different backgrounds, not all science and technical degrees
S2a | Erin Trouba and Elizabeth Grant With floaters - Allyson Gibson (Lancaster County), Angie Bowman (NRCS), Susan Parry (NRCS), Suzanna Trevena (EPA) | To find ways to diversify current staff in the conservation sector, including hires with different educational and training backgrounds, as well as other identity features such as race, ethnicity, physical ability, etc. | Perform a workforce analysis to understand what the current workforce looks like and where new employees are coming from. Questions to include in analysis: What are the current vacancies in the conservation sector within Pennsylvania? What are the qualifications needed for those jobs? What training is provided on-the-job? Is someone who is in similarly titled positions doing the same tasks? Work with agencies and organization that are already doing this kind of research. The Department of Labor and Industry along with local county Chambers of Commerce would have good insight into local workforce. | EPA; USDA-NRCS, Office of Administration - chief diversity officer, DEP Office of Environmental Justice | Medium priority; long term project; begin immediately | Who is leaving the workforce? To go where? | Gathering and synthesizing this data will help to address unknowns for multiple action items; Dept of Labor or similar entities as key contributors
|  |  | Analysis of Job advertisements to understand how to make the job open to more people with different backgrounds. Some job posting advertisements may be unintentionally limiting. Analyze job postings to make sure they seem open to different backgrounds. Having the perspective of an HR agency would be helpful for this recommendation. Using the results of the analysis to create best practices that partners can use to make their job posting more inclusive or welcoming . These practices would ensure that groups of people don’t exclude themselves from applying for these job openings due to having non typical education, experience, and background for the conservation sector. | Individual conservation organizations and entities can self-evaluate; guidance can be provided by key oversight organizations | Medium priority; near term project; begin immediately |  | Example questions to ask: where are positions being advertised, what is in the job descriptions?
S2b
S2c |  |  | Individual organization hiring analysis: Identify a broader target audience, general outreach and awareness on social media, participate in job fairs and events. | Individual conservation organizations and entities can self-evaluate; guidance and support can be provided by key oversight organizations | Medium priority; near term project; begin immediately
Priority Action Item: Regionalization: Regionalize staff, especially for smaller conservation districts and planning commissions
| Teddi Stark, Josh Glace, and Karen Books | Creating a regionalized staff position in addition to current conservation district staff could have many benefits especially for smaller conservation districts and planning commissions. | Create an office similar to the state district office that would be available to assist every county with technical, administration, legal, and HR work. Staff of this office would be available to assist with big projects, when turnover occurs, and have specialized knowledge in different fields. This office could serve as a next step for county conservation district and other conservation staff once they have reached the top of their current organization. | Create a focus group with members DEP, SCC Program Areas CAPs, Planning Commissions | Start immediately - knowing it will take time to see progress | Where would the funding come from? This would be a main focus of the focus group Location - regional, statewide ?
S3a
S3b |  |  | Survey the conservation districts to find what kind of regional staff would be the most helpful to them. This could be done in a regional district manager meeting, a survey sent to the districts, or a scheduled webinar. | DEP, SCC Program Areas CAPs, Planning Commissions | High priority - near term project to start immediately
Priority Action Item: Cross train to build on employee knowledge to keep programs and projects running when turnover happens
| Elizabeth Grant, Josh Glace, Willie Null | Encourage the prioritization of cross training to build on employee knowledge to keep operations running smoothly when turnover happens. Not just focusing on conservation districts, planning commissions, coordinator contractors, but all partners working in counties for clean water. Prioritizing cross training can be beneficial not just in times of turnover but also consider operational benefits for other transitions, time off, etc. | Create regional floating staff positions that can step in when turnover occurs. This regional staff member would not taking the place of staff in the district but in addition to them. Could have working knowledge of different programs within the conservation districts to fills gaps in times of need. Staff members could cover different areas (Ag, Permitting, Stormwater, HR). Staff could also be available to help train and onboard new staff | Create a focus group with members from DEP, SCC, Conservation Districts, PACD, etc. | Medium priority - near term project | Creating a regional floating positions would be determined on equitable distribution and duration of staff support and whether these positions could also assist more broadly with CAP implementation (outside of CD departmental needs?) What would the job description be and what experience/qualifications would be desired?
S4a
S4b |  |  | Streamlining grant requirements, invoicing, and reporting for both state and federal grant programs. This would allow conservation district staff to have more time in their day for crossing training to occur. | Legislative and policy component to this, Office of Administration - CODE PA | Top priority - start immediately
S4c |  |  | A mindset shift at the conservation district level, specifically conservation district managers to allow cross training to be a priority. This could be a large culture shift for a district/organization depending on the existing culture. Training could be provided for the conservation district managers to create this mindset in the organization. Change will be needed on the state and federal level to allow multiple district staff to work on the same program (102, dirt and gravel roads, etc.) This will keep staff jobs interesting, allow for staff knowledge across programs, and program work to be done more efficiently | DEP, Chesapeake Bay Program, Dirt and gravel roads (to allow more flexibility within the programs to allow for more cross training) | Top priority - start immediately
Priority Action Item: Allocate dedicated funding annually to counties to stabilize and assure steady workload for staff/Funding for more administrative/program staffing to help manage all of the grants
| Erica Tomlinson, Karen Books, Kristen Wolf, Erin Letavic | County partners have proven that there is more grant related administrative work than staff to complete it. Establishing a dedicated long-term funding source and specific amount of funding for this work can help stabilize the workload and planning. | Simplify the administrative workload on counties by combining and streamlining grant applications, requirements, invoicing, and reporting on the state and federal level. There is a legislative and policy component to this that will need to be looked into further. | Legislative and policy component to this - Office of Administration - CODE PA, Grantors (federal and state), Executive leadership | High priority - near term project to start immediately
S5a
|  |  | Provide a funding source for administrative staff. This funding could be administered through a state agency to a contractor who would provide the resources directly to the county, similar to how technical assistances has been provided in the past. This staff would need experience and training in: contracting , financial oversight, grant management, understanding of federal and state grant requirements, wage and contract requirements, application and reporting deadlines and requirements. Might possibly tie into the regionalized position Action Item. | Create a focus group with members from DEP, SCC, Conservation Districts, PACD, etc. | High priority - near term project to start immediately
S5b