## Technical and Administrative
Final Recommendation: Technical and Administrative Assistance Progress Team Strategies for Success
The ISSUE(s) were identified at the Clean Water Gathering - Progress Teams identified 15 PRIORITIES to be taken to address the issues - Priority Action Members developed a strategy to successfully accomplish the priority action item ie. Strategies for Success
Staff Building and Retention Progress Team members:
Numbering corresponding to SSM | Progress Team Priority Action Members | Scope of the Priority Action Item | How should action be taken? What are the steps needed for action? How could the action steps be funded? | Who is required to take action? Who has the authority to support the action? What agencies need to be involved? Who can move this forward? Who can get this unstuck? | When should action be taken? What is the priority level? Is this something that is a near-term/long-term project? Can this be addressed immediately? | Unknowns that will need to be addressed | Additional Comments
Priority Action Item: Engineering assistance is needed
T1a | Kate Bresaw, Jennifer Fetter, Jason Fellon, Jay Patel, Chris Canfield | Conduct a gap assessment of engineering providers to determine areas of improvement. | • Financial support is needed • Hire someone to do the survey work •Create a scope of work that a gap assesment should be based off of. | • DEP/SCC would be needed for financial support • The company that will be doing the GAP assessment will need to look at the public and private sectors as well as NGO's | • Looking that the 2025 - 2026 fiscal year seems like the most logical timeframe | Scope of works are very detailed and time comsuming. This fact needs to be thought about before commiting to it. | TD - Start thinking of the questions that should be asked in this gap assessment. This should be in the HOW section.
T1b |  | Outreach to non-ag engineers to increase the amount of engineers doing work in the field. | i.Engineer Conferences, etc. •Consult with engineers that have made the transition and develop outreach strategy around their recommendations ii.Mentoring (provide financial support for the Mentor) •ACES •Other engineering firms that have made the transition | •DEP •SCC •CACAT | Now
T1c |  | Outreach to near term engineering graduates to educate them on the conservation/agricultural engineering field. This will hopefully increase the amount of engineers in the field. | i. Connections with Post-secondary civil and eng. Programs to promote conservation and ag. opportunities | •DEP •SCC •CACAT | Now
T1d |  | Support engineering programs that currently exist. Such as: •CB Engineers •CB Techs •TAG Engineers • Practice Approval System (PAS) Program (SCC/CACAT) •TAP (DEP) | i. Identify alternate funding sources for any expiring funds: 1. COVID/ARPA 2. IIJA ii. Prioritize core programs in CBRAP/CBIG/GG 1. CB Engineers 2. CB Techs 3. TAG Engineers | •DEP •SCC | Now
T1e |  | Form a stakeholder workgroup to explore a change to state The Engineer, Land Surveyor and Geologist Registration Law (Act 367) exemption to state employees (not just federal) | •Recommend to Lawmakers/Government Organizations | •Lawmakers •Governement Organizations PACD? | •When lawmakers determine that it is a priority
Priority Action Item: Streamline and centralize reporting
T2a | Kate Bresaw, Josh Longmore, Mike LaSala | Reverification of BMPs outside of PK and FieldDoc | •Directive from Adminstration to have this discussion •Develop centralized guidance around required attributes | •DEP Secretary •BWRNM and all data reporters to develop individualized reverification plans for each data reporter | •Now
T2b |  | Commonwealth Programs should review reporting expectations to evaluate and determine real need from CCDs for the data reported | Directive/program decidion to undergo the evaluation Uniform guide to make evaluation consistent (to be used by all programs) | •DEP/PDA Secretaries •Staff to complete directive | •With every delegation agreement/contract cycle? |  | Some of these reports have not changed in 10, 12, or 15 years.
T2c |  | Programs should move toward same/connect mechanism(s) for reporting whatever is needed from CCDs | •Directive/program decision •Update guidance for CCD staff accordingly | •Program staff (to talk to each other) •CCD staff (to provide feedback and test) | •After reporting evaluations are complete (as a product of those evaluations) in number 2
Priority Action Item: How to provide more structured approach to private/public partnerships
T3a | Andrew Gavin, Harry Campbell, Tyler Neimond, Jason Fellon | Create a framework of key elements that are needed to make a successful partnership. •List of existing partnerships with mission statements, key people, and contact information | 1. Two step process for creating a successful partnership a. Ask philosophical questions a. Why did these groups come together b. How did they come together c. Why are they staying together i. Mission overlap 2. How do these partnerships codify their relationship/partnership a. How will they operate together 3. Have someone compile lists of partnership 4. Have that same person catalog each partnership 5. Find successful partnerships within the compiled list 6. Inventory common elements held by those successful partnerships a. Sustainable funding b. Capacity of partnership c. Mission overlap/Common themes d. Flexibility of Partnership e. Longevity of mission? Or Partners? • Model similar to the progress teams or CAP | • Agencies funding these types of projects • State employee that has time carved out for this type of work | As soon as possible Revisited on a reoccuring basis (annually, biannually?) | Not sure what type of mechanism this would be (portal, website, document) to get these organizations together to create these partnerships. This mechanism also needs someone to house and handle this information.
T3b |  | Conduct a gap assessment of partnerships in the Chesapeake Bay Watershed Region | 1. Formation of group that oversees the hired consultant 2. Hire Consultant to complete Gap Assessment 3. Questions you would like answered by this Gap Assessment a. See where BMP implementation pace is not meeting expectation a. What is the inhibiting factor that is creating this problem § Bottleneck b. Survey of partnerships to identify needs c. Funding distribution analysis 4. Facilitated discussion on how the Gap Assessment can help? a. Lead to recommendations on how to bolster existing partnership or formulate new partnerships to accelerate implementation | • Representative steering group • State government agencies • local government • NGOs • Non-profits • For profit companies Hired consultant | Follow the completion of the first recommendation |  | TD - Start thinking of the questions that should be asked in this gap assessment. This should be in the HOW section.
Priority Action Item: Increase support and resources for project prioritization and timeline management
T4a | Mike LaSala, Matt Kofroth, Andrew Gavin, Harry Campbell, Jennifer Fetter, Jason Fellon | Create information database (preferably merge with D&G Roads/ACAP) to facilitate the flow of ideas and information from county to county. Doing this will allow counties to plan projects for the future construction seasons. Allowing for better timeline management. | Bring together SCC, CACAT, and DEP to discuss the timing of this application. | • SCC • CACAT • DEP • "Champion" • Tri Secretaries | • Beginning of 2025
T4b |  | Advocate for a more stable amount of project implementation funding that gives practitioners the ability to plan for the future as well as have readaliy available funding throught project implementation. | • Bringing topic up whenever possible • Funding recipients • Having the metrics on what the funding delivered • Matching funds brought in by using the grant funding • Funders have some level of coordination Keep the rhythm going on selected priority project installation | • Conservations Districts • NGOs • Funders • SRBC • DEP • NFWF • DCNR
Priority Action Item: Block permitting applications for watershed or specific project types
T5a | Jay Patel, Mike LaSala | To convene a group of practitioners and policy individuals to determine if the concept of block permitting or expansion of GPs is feasible. | • Define what "block permitting" is • Define what issue block permitting is intended to fix • Identify if expanding the General Permit suite in the 102 and 105 programs would facilitate addressing the issue | • DEP • CDs • Practitioners • Potential Project Sponsors |  |  | Some of these reports have not changed in 10, 12, or 15 years.