## Slide 1: Dairy Farmers of America PEDA 2014 Project
PEDA Board Meeting
May 18, 2015

## Slide 2
DFA is a national milk marketing cooperative (dairy farmer-owned)
Own 33 plants in the U.S.
Middlebury Center, Tioga County
  55 Employees, hired 3 new employees in 2015 due to increased operations
  Main product is powdered milk used by their customers in the production of many food products. Also produce skim milk condense and cream, and specialty milk powders.
Dairy Farmers of America Overview

## Slide 3
Removal of 25 year-old mechanical burner, linkage and gas train (high maintenance costs)
Install new electronic controlled burner, VFD for blower motor, and new gas train to reduce electric consumption
Install an economizer on boiler feed water in order to reduce the amount of energy needed to produce steam for their processes
Overview of PEDA Project

## Slide 4
Work began January 2015, and was completed February 2015
The project took just 1 month to complete
CSI Services, York, PA was the contractor used
  A total of 471 man-hours spent on the job (3-5 laborers)
Project Timeline

## Slide 5
PEDA 2014 Grant: $75,976
Matching Funds: $75,976 (50%)
Total Project Cost: $151,952
Project Cost

## Slide 6
25-Year Old Mechanical Burner

## Slide 7
25-Year Old Mechanical Burner

## Slide 8: Burner linkage
Old Mechanical Burner Linkage

## Slide 9
Old Boiler Stack

## Slide 10
New Electronic-Controlled Burner

## Slide 11
New Burner

## Slide 12
Economizer

## Slide 13
Finished Project

## Slide 14
Before & After

## Slide 15
The economizer was very difficult to place due to its size. Some of the steam lines had to be cut in order to fit the economizer in.
New air vents need to be added to the boiler room in order to allow adequate air flow for the boiler intake
But, overall, things went smoothly with the installation
Difficulties/ “Bumps in the Road”

## Slide 16
Natural gas and electric savings
  averaging 400 DTH (400 MMBTU) /month
The new burner is expected to save approximately $70,000/year
The new economizer is expected to save approximately $20,000/year
The expected payback is <2 years
The burner is running at about 1/3 of its firing potential—it is extremely efficient.
Project Payback and Savings

## Slide 17: Michelle Ferguson DEP Northcentral Region miferguson@pa.gov 570-327-3783