## Southwest
Requests to Backfill Trenches - More Than 10 Days Needed- Southwest
Spread | Station Start | Station End | Footage | Description | Projected Start Date | Projected Date of Backfill Completion | Reason/Justification | LAT Start | LONG Start | LAT End | LONG End | Municipality | County | DEP Region
PPP2 | 269550 | 2697+50 | 200 | CIS of Violet Ln. | TBD when weather allows | 30 Days after Approval to Proceed by DEP | Delmont Station Tie-Ins - Excavation Depth Greater than 10 ft. (Currently Benched Back) - Unsafe | 40.4296 | -79.5738 | 40.4289 | -79.5731 | Salem | Westmoreland | Southwest
PPP2 | 277140 | 277190 | 50 | Church St HDD | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4256 | -79.5482 | 40.4256 | -79.5481 | Salem Township | Westmoreland | Southwest
PPP2 | 277400 | 277420 | 20 | GAS of Church St | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4255 | -79.5473 | 40.4255 | -79.5472 | Salem Township | Westmoreland | Southwest
PPP2 | 304417 | 304580 | 163 | GAS of Koontze Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4361 | -79.4566 | 40.4362 | -79.4561 | Loyalhanna Township | Westmoreland | Southwest
PPP2 | 310945 | 311118 | 173 | GAS of Bush Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.438 | -79.4336 | 40.438 | -79.4329 | Loyalhanna Township | Westmoreland | Southwest
PPP2 | 311971 | 312025 | 54 | GAS of Bush Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4381 | -79.4299 | 40.4381 | -79.4297 | Loyalhanna Township | Westmoreland | Southwest
PPP2 | 312467 | 312500 | 33 | Loyalhanna Creek | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4381 | -79.4281 | 40.4381 | -79.428 | Loyalhanna Township | Westmoreland | Southwest
PPP2 | 352605 | 352634 | 29 | CIS of airport Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4462 | -79.2917 | 40.4463 | -79.2916 | Burrell Township | Indiana | Southwest
PPP2 | 354504 | 354545 | 41 | GAS of Newport Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4481 | -79.2854 | 40.4482 | -79.2853 | Burrell Township | Indiana | Southwest
PPP2 | 372860 | 372955 | 95 | GAS of Kendall RD | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4525 | -79.2223 | 40.4525 | 79.222 | Burrell Township | Indiana | Southwest
PPP2 | 374979 | 375080 | 101 | GAS of Kendall RD | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4532 | -79.2153 | 40.4534 | -79.2149 | Burrell Township | Indiana | Southwest
PPP2 | 394450 | 394500 | 50 | GAS of Chestnutt Ridge | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.439 | -79.1526 | 40.439 | -79.1524 | Burrell Township | Indiana | Southwest
PPP2 | 405596 | 405748 | 152 | GAS of Hwy 259 | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4361 | -79.1134 | 40.4361 | -79.1128 | West Wheatfield Township | Indiana | Southwest
PPP2 | 410172 | 410208 | 36 | CIS of Harry Boring Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4345 | -79.0973 | 40.4345 | -79.0972 | West Wheatfield Township | Indiana | Southwest
PPP2 | 410900 | 410950 | 50 | CIS of Harry Boring Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4344 | -79.0947 | 40.4344 | -79.0946 | West Wheatfield Township | Indiana | Southwest
PPP2 | 417894 | 417991 | 97 | CIS of Bethel Cemetery Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4328 | -79.0698 | 40.4328 | -79.0695 | West Wheatfield Township | Indiana | Southwest
PPP2 | 421244 | 421383 | 139 | GAS of Clay Pike Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4322 | -79.0586 | 40.4322 | -79.0581 | East Wheatfield Township | Indiana | Southwest
PPP2 | 421577 | 421981 | 404 | GAS of Clay Pike Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4322 | -79.0574 | 40.4321 | -79.0559 | East Wheatfield Township | Indiana | Southwest
PPP2 | 422133 | 422248 | 115 | GAS of Clay Pike Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4321 | -79.0554 | 40.4321 | -79.055 | East Wheatfield Township | Indiana | Southwest
PPP2 | 424156 | 424334 | 178 | CIS of Hutchison Hollow Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4317 | -79.0481 | 40.4316 | -79.0475 | East Wheatfield Township | Indiana | Southwest
PPP2 | 425995 | 426085 | 90 | CIS of Hutchison Hollow Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4315 | -79.0415 | 40.4315 | -79.0412 | East Wheatfield Township | Indiana | Southwest
PPP2 | 427630 | 427846 | 216 | GAS of Hutchison Hollow Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4313 | -79.0358 | 40.4313 | -79.0351 | East Wheatfield Township | Indiana | Southwest
PPP2 | 428666 | 428740 | 74 | GAS of Hutchison Hollow Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4312 | -79.0321 | 40.4312 | -79.0319 | East Wheatfield Township | Indiana | Southwest
PPP2 | 434385 | 4344+35 | 50 | GAS of Falloon Hallow | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4304 | -79.0123 | 40.4303 | -79.0122 | East Wheatfield Township | Indiana | Southwest
PPP2 | 436238 | 436927 | 689 | CIS of Grange Hall Rd | Weather Permitting | 4 days | Cannot properly backfill due to snow in the ditch | 40.4305 | -79.0057 | 40.4305 | -79.0033 | East Wheatfield Township | Indiana | Southwest
PPP2 | 436988 | 437051 | 63 | CIS of Grange Hall Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4305 | -79.0031 | 40.4305 | -79.0028 | East Wheatfield Township | Indiana | Southwest
PPP2 | 441037 | 441172 | 135 | GAS of SR403 | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.431 | -78.9903 | 40.431 | -78.9898 | East Wheatfield Township | Indiana | Southwest
PPP2 | 441456 | 441702 | 246 | GAS of SR403 | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.431 | -78.9888 | 40.4314 | -78.9881 | East Wheatfield Township | Indiana | Southwest
PPP2 | 442706 | 442864 | 158 | CIS of Deyarmin Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4334 | -78.9857 | 40.4337 | -78.9853 | East Wheatfield Township | Indiana | Southwest
PPP2 | 443799 | 444115 | 316 | GAS of Deyarmin | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4332 | -78.982 | 40.4331 | -78.9809 | East Wheatfield Township | Indiana | Southwest
PPP2 | 444997 | 445118 | 121 | GAS of Deyarmin | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4326 | -78.9778 | 40.4325 | -78.9774 | East Wheatfield Township | Indiana | Southwest
PPP2 | 445680 | 445720 | 40 | CIS of Thomas Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4324 | -78.9754 | 40.4324 | -78.9752 | East Wheatfield Township | Indiana | Southwest
PPP2 | 445847 | 445901 | 54 | CIS of Thomas Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4325 | -78.9748 | 40.4326 | -78.9746 | East Wheatfield Township | Indiana | Southwest
PPP2 | 446721 | 447434 | 713 | CIS of Thomas Rd | Weather Permitting | 5 days | Cannot properly backfill due to snow in the ditch | 40.4331 | -78.9717 | 40.4334 | -78.9692 | East Wheatfield Township | Indiana | Southwest
PPP2 | 447523 | 447822 | 299 | CIS of Thomas Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4333 | -78.969 | 40.4327 | -78.9684 | East Wheatfield Township | Indiana | Southwest
PPP2 | 448352 | 448384 | 32 | GAS of Thomas Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4314 | -78.9677 | 40.4313 | -78.9676 | East Wheatfield Township | Indiana | Southwest
PPP2 | 448871 | 449132 | 261 | GAS of Thomas Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4311 | -78.9659 | 40.4309 | -78.965 | East Wheatfield Township | Indiana | Southwest
PPP2 | 449616 | 449980 | 364 | GAS of Thomas Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4307 | -78.9633 | 40.4305 | -78.962 | East Wheatfield Township | Indiana | Southwest
PPP2 | 450120 | 450153 | 33 | GAS of Thomas Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4305 | -78.9615 | 40.4305 | -78.9614 | East Wheatfield Township | Indiana | Southwest
PPP2 | 450335 | 450626 | 291 | GAS of Thomas Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4305 | -78.9607 | 40.4303 | -78.9597 | East Wheatfield Township | Indiana | Southwest
PPP2 | 450722 | 450745 | 23 | GAS of Thomas Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4302 | -78.9594 | 40.4302 | -78.9594 | East Wheatfield Township | Indiana | Southwest
PPP2 | 452124 | 452156 | 32 | GAS of Thomas Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4296 | -78.9547 | 40.4296 | -78.9546 | East Wheatfield Township | Indiana | Southwest
PPP2 | 452187 | 452227 | 40 | GAS of Thomas Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4296 | -78.9545 | 40.4296 | -78.9543 | East Wheatfield Township | Indiana | Southwest
PPP2 | 455521 | 455840 | 319 | GAS of Thomas Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4269 | -78.9431 | 40.4267 | -78.942 | Jackson Township | Cambria | Southwest
PPP2 | 460496 | 460589 | 93 | CIS of Dishong Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4248 | -78.9255 | 40.4248 | -78.9251 | Jackson Township | Cambria | Southwest
PPP2 | 460872 | 461636 | 764 | CIS of Dishong Mountain Rd | Weather Permitting | 5 days | Cannot properly backfill due to snow in the ditch | 40.4247 | -78.9241 | 40.4244 | -78.9214 | Jackson Township | Cambria | Southwest
PPP2 | 461925 | 462295 | 370 | CIS of Dishong Mountain Rd | Weather Permitting | 4 days | Cannot properly backfill due to snow in the ditch | 40.4242 | -78.9204 | 40.4241 | -78.9191 | Jackson Township | Cambria | Southwest
PPP2 | 462637 | 463058 | 421 | CIS of Dishong Mountain Rd | Weather Permitting | 4 days | Cannot properly backfill due to snow in the ditch | 40.4239 | -78.9179 | 40.4237 | -78.9164 | Jackson Township | Cambria | Southwest
PPP2 | 463486 | 465215 | 1729 | CIS of Dishong Mountain Rd | Weather Permitting | 10 Days | Cannot properly backfill due to snow in the ditch | 40.4234 | -78.915 | 40.4226 | -78.9088 | Jackson Township | Cambria | Southwest
PPP2 | 472388 | 473463 | 1075 | CIS of Benshoff Hill Rd | Weather Permitting | 7 days | Cannot properly backfill due to snow in the ditch | 40.4192 | -78.8835 | 40.4183 | -78.8799 | Jackson Township | Cambria | Southwest
PPP2 | 480029 | 480569 | 540 | GAS of William Penn Ave | Weather Permitting | 5 days | Cannot properly backfill due to snow in the ditch | 40.4156 | -78.8572 | 40.4156 | -78.8553 | Jackson Township | Cambria | Southwest
PPP2 | 481129 | 481210 | 81 | GAS of William Penn Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4164 | -78.8536 | 40.4165 | -78.8533 | Jackson Township | Cambria | Southwest
PPP2 | 481972 | 482095 | 123 | GAS of William Penn Ave | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4172 | -78.8507 | 40.4173 | -78.8503 | Jackson Township | Cambria | Southwest
PPP2 | 482757 | 482830 | 73 | GAS of William Penn Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4179 | -78.8481 | 40.4179 | -78.8478 | Jackson Township | Cambria | Southwest
PPP2 | 483006 | 483115 | 109 | GAS of William Penn Ave | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4181 | -78.8472 | 40.4182 | -78.8468 | Jackson Township | Cambria | Southwest
PPP2 | 483304 | 483417 | 113 | GAS of William Penn Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4183 | -78.8462 | 40.4184 | -78.8458 | Jackson Township | Cambria | Southwest
PPP2 | 483837 | 483909 | 72 | CIS of Adams Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4188 | -78.8444 | 40.4188 | -78.8441 | Jackson Township | Cambria | Southwest
PPP2 | 484016 | 484085 | 69 | CIS of Adams Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4189 | -78.8438 | 40.419 | -78.8435 | Jackson Township | Cambria | Southwest
PPP2 | 484293 | 484367 | 74 | CIS of Adams Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4191 | -78.8428 | 40.4192 | -78.8425 | Jackson Township | Cambria | Southwest
PPP2 | 485302 | 485328 | 26 | CIS of Adams Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4198 | -78.8393 | 40.4198 | -78.8392 | Jackson Township | Cambria | Southwest
PPP2 | 487083 | 487171 | 88 | GAS of Adams Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.421 | -78.8333 | 40.4211 | -78.8329 | Jackson Township | Cambria | Southwest
PPP2 | 487515 | 487810 | 295 | GAS of Adams Ave | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4213 | -78.8317 | 40.4216 | -78.8307 | Jackson Township | Cambria | Southwest
PPP2 | 488986 | 489066 | 80 | GAS of Adams Ave | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4224 | -78.8267 | 40.4225 | -78.8264 | Jackson Township | Cambria | Southwest
PPP2 | 492392 | 492486 | 94 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4252 | -78.815 | 40.4253 | -78.8147 | Jackson Township | Cambria | Southwest
PPP2 | 493390 | 493410 | 20 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.426 | -78.8116 | 40.426 | -78.8115 | Jackson Township | Cambria | Southwest
PPP2 | 493686 | 493758 | 72 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4262 | -78.8105 | 40.4263 | -78.8103 | Jackson Township | Cambria | Southwest
PPP2 | 493898 | 493996 | 98 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4264 | -78.8098 | 40.4265 | -78.8095 | Jackson Township | Cambria | Southwest
PPP2 | 494238 | 494335 | 97 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4267 | -78.8086 | 40.4267 | -78.8083 | Jackson Township | Cambria | Southwest
PPP2 | 494411 | 494507 | 96 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4268 | -78.808 | 40.4269 | -78.8077 | Jackson Township | Cambria | Southwest
PPP2 | 494901 | 495068 | 167 | GAS of Swiggle Mountain Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4272 | -78.8064 | 40.4273 | -78.8058 | Jackson Township | Cambria | Southwest
PPP2 | 495590 | 495620 | 30 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4278 | -78.804 | 40.4279 | -78.8039 | Jackson Township | Cambria | Southwest
PPP2 | 495924 | 496024 | 100 | GAS of Swiggle Mountain Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4282 | -78.8029 | 40.4283 | -78.8026 | Jackson Township | Cambria | Southwest
PPP2 | 497367 | 497551 | 184 | GAS of Swiggle Mountain Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4294 | -78.798 | 40.4296 | -78.7974 | Jackson Township | Cambria | Southwest
PPP2 | 497745 | 498110 | 365 | GAS of Swiggle Mountain Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4297 | -78.7967 | 40.43 | -78.7954 | Jackson Township | Cambria | Southwest
PPP2 | 498430 | 498987 | 557 | CIS of Rorabaugh Rd | Weather Permitting | 4 days | Cannot properly backfill due to snow in the ditch | 40.4302 | -78.7943 | 40.4307 | -78.7924 | Jackson Township | Cambria | Southwest
PPP2 | 501629 | 501900 | 271 | GAS of Rorabaugh Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4327 | -78.7833 | 40.4329 | -78.7824 | Cambria Township | Cambria | Southwest
PPP2 | 509573 | 509659 | 86 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4389 | -78.7572 | 40.439 | -78.7569 | Cambria Township | Cambria | Southwest
PPP2 | 511555 | 511650 | 95 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4407 | -78.7505 | 40.4408 | -78.7502 | Cambria Township | Cambria | Southwest
PPP2 | 511705 | 511742 | 37 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4408 | -78.75 | 40.4409 | -78.7499 | Cambria Township | Cambria | Southwest
PPP2 | 512059 | 512092 | 33 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4411 | -78.7488 | 40.4411 | -78.7487 | Cambria Township | Cambria | Southwest
PPP2 | 512203 | 512306 | 103 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4412 | -78.7483 | 40.4413 | -78.7479 | Cambria Township | Cambria | Southwest
PPP2 | 513235 | 513309 | 74 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4419 | -78.7447 | 40.442 | -78.7444 | Cambria Township | Cambria | Southwest
PPP2 | 513503 | 513593 | 90 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4421 | -78.7438 | 40.4422 | -78.7435 | Cambria Township | Cambria | Southwest
PPP2 | 514542 | 514632 | 90 | GAS of New Germany Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4428 | -78.7402 | 40.4429 | -78.7398 | Cambria Township | Cambria | Southwest
PPP2 | 515669 | 515957 | 288 | GAS of Fairlane Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4436 | -78.7363 | 40.4439 | -78.7353 | Cambria Township | Cambria | Southwest
PPP2 | 516167 | 516744 | 577 | GAS of Fairlane Rd | Weather Permitting | 6 days | Cannot properly backfill due to snow in the ditch | 40.444 | -78.7345 | 40.4445 | -78.7326 | Cambria Township | Cambria | Southwest
PPP2 | 516859 | 516905 | 46 | GAS of Fairlane Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4446 | -78.7322 | 40.4446 | -78.732 | Cambria Township | Cambria | Southwest
PPP2 | 517634 | 518938 | 1304 | GAS of Fairlane Rd | Weather Permitting | 5 days | Cannot properly backfill due to snow in the ditch | 40.4451 | -78.7295 | 40.4461 | -78.725 | Cambria Township | Cambria | Southwest
PPP2 | 519801 | 520256 | 455 | GAS of Fairlane Rd | Weather Permitting | 5 days | Cannot properly backfill due to snow in the ditch | 40.4468 | -78.722 | 40.4472 | -78.7204 | Cambria Township | Cambria | Southwest
PPP2 | 520317 | 520755 | 438 | GAS of Fairlane Rd | Weather Permitting | 5 days | Cannot properly backfill due to snow in the ditch | 40.4472 | -78.7202 | 40.4475 | -78.7187 | Cambria Township | Cambria | Southwest
PPP2 | 521223 | 521403 | 180 | GAS of Fairlane Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4479 | -78.7171 | 40.4481 | -78.7165 | Cambria Township | Cambria | Southwest
PPP2 | 521410 | 521529 | 119 | GAS of Fairlane Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4481 | -78.7165 | 40.4482 | -78.7161 | Cambria Township | Cambria | Southwest
PPP2 | 522000 | 5221+12 | 112 | GAS of Fairlane Rd | Weather Permitting | 25 Days after Approval to Proceed by DEP and after PPP2 is complete, hydro'd and dried. | Ebensburg Station Tie-Ins - Excavation Depth Greater than 14 ft. (Currently Benched Back) - Unsafe | 40.4486 | -78.7145 | 40.4489 | -78.7147 | Cambria | Cambria | Southwest
PPP2 | 522089 | 522112 | 23 | GAS of Fairlane Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4489 | -78.7146 | 40.4489 | -78.7147 | Cambria Township | Cambria | Southwest
PPP2 | 522178 | 522197 | 19 | GAS of Fairlane Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4491 | -78.7147 | 40.4491 | -78.7148 | Cambria Township | Cambria | Southwest
PPP2 | 522858 | 522975 | 117 | GAS of Wilmore Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4492 | -78.7115 | 40.4493 | -78.7111 | Cambria Township | Cambria | Southwest
PPP2 | 522995 | 523591 | 596 | GAS of Wilmore Rd | Weather Permitting | 6 days | Cannot properly backfill due to snow in the ditch | 40.4493 | -78.711 | 40.4498 | -78.709 | Cambria Township | Cambria | Southwest
PPP2 | 524451 | 524826 | 375 | GAS of Wilmore Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4505 | -78.706 | 40.4508 | -78.7047 | Cambria Township | Cambria | Southwest
PPP2 | 525064 | 525473 | 409 | GAS of Wilmore Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.451 | -78.7039 | 40.4513 | -78.7025 | Cambria Township | Cambria | Southwest
PPP2 | 525690 | 525896 | 206 | GAS of Wilmore Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4515 | -78.7018 | 40.4516 | -78.701 | Cambria Township | Cambria | Southwest
PPP2 | 526218 | 527488 | 1270 | GAS of Wilmore Rd | Weather Permitting | 10 Days | Cannot properly backfill due to snow in the ditch | 40.4519 | -78.7 | 40.4523 | -78.6955 | Cambria Township | Cambria | Southwest
PPP2 | 527606 | 528148 | 542 | GAS of Wilmore Rd | Weather Permitting | 4 days | Cannot properly backfill due to snow in the ditch | 40.4524 | -78.695 | 40.4524 | -78.6931 | Cambria Township | Cambria | Southwest
PPP2 | 531519 | 531564 | 45 | CIS of Patrick Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4525 | -78.681 | 40.4525 | -78.6808 | Munster Township | Cambria | Southwest
PPP2 | 531980 | 532048 | 68 | GAS of Spinner Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4525 | -78.6793 | 40.4525 | -78.6791 | Munster Township | Cambria | Southwest
PPP2 | 533742 | 533901 | 159 | GAS of Patricks Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4524 | -78.673 | 40.4524 | -78.6724 | Munster Township | Cambria | Southwest
PPP2 | 534504 | 535343 | 839 | GAS of Patricks Rd | Weather Permitting | 4 days | Cannot properly backfill due to snow in the ditch | 40.4524 | -78.6704 | 40.4524 | -78.6674 | Munster Township | Cambria | Southwest
PPP2 | 536726 | 5367+76 | 50 | GAS of Munster Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4525 | -78.6625 | 40.4524 | -78.6623 | Munster Township | Cambria | Southwest
PPP2 | 537011 | 5371+11 | 100 | GAS of Munster Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4525 | -78.6615 | 40.4525 | -78.6611 | Munster Township | Cambria | Southwest
PPP2 | 537288 | 5373+88 | 100 | CIS of Gailey Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4525 | -78.6605 | 40.4525 | -78.6601 | Munster Township | Cambria | Southwest
PPP2 | 537476 | 5375+26 | 50 | CIS of Gailey Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4525 | -78.6598 | 40.4526 | -78.6596 | Munster Township | Cambria | Southwest
PPP2 | 538054 | 538261 | 207 | CIS of Gailey Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4525 | -78.6578 | 40.4525 | -78.6571 | Munster Township | Cambria | Southwest
PPP2 | 539297 | 539458 | 161 | GAS of Gailey Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.453 | -78.6537 | 40.4531 | -78.6531 | Munster Township | Cambria | Southwest
PPP2 | 539754 | 539781 | 27 | GAS of Gailey Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4527 | -78.6522 | 40.4526 | -78.6521 | Munster Township | Cambria | Southwest
PPP2 | 548214 | 548322 | 108 | GAS of Cooney Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4539 | -78.622 | 40.4539 | -78.6216 | Munster Township | Cambria | Southwest
PPP2 | 548341 | 548562 | 221 | GAS of Cooney Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4539 | -78.6216 | 40.454 | -78.6208 | Munster Township | Cambria | Southwest
PPP2 | 548931 | 549149 | 218 | GAS of Cooney Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4541 | -78.6195 | 40.4541 | -78.6187 | Cresson Township | Cambria | Southwest
PPP2 | 549617 | 549756 | 139 | GAS of Cooney Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4542 | -78.617 | 40.4542 | -78.6165 | Cresson Township | Cambria | Southwest
PPP2 | 552098 | 552124 | 26 | GAS of Cooney Rd | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4512 | -78.6092 | 40.4511 | -78.6091 | Cresson Township | Cambria | Southwest
PPP2 | 552297 | 552360 | 63 | CIS of SR 53 | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4509 | -78.6085 | 40.4508 | -78.6083 | Cresson Township | Cambria | Southwest
PPP2 | 553945 | 554006 | 61 | CIS of SR 53 | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4484 | -78.6036 | 40.4483 | -78.6037 | Cresson Township | Cambria | Southwest
PPP2 | 554958 | 555075 | 117 | CIS of SR 53 | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4463 | -78.6034 | 40.4462 | -78.6031 | Cresson Township | Cambria | Southwest
PPP2 | 555453 | 555577 | 124 | GAS of SR 53 | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4456 | -78.6019 | 40.4454 | -78.6015 | Cresson Township | Cambria | Southwest
PPP2 | 555789 | 555894 | 105 | GAS of SR 53 | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4453 | -78.6009 | 40.4454 | -78.6005 | Cresson Township | Cambria | Southwest
PPP2 | 555820 | 555920 | 100 | GAS of SR 53 | Weather Permitting | 1 Day | Cannot properly backfill due to snow in the ditch | 40.4453 | -78.6008 | 40.4454 | -78.6004 | Cresson Township | Cambria | Southwest
PPP2 | 555923 | 556127 | 204 | GAS of SR 53 | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4454 | -78.6004 | 40.4455 | -78.5997 | Cresson Township | Cambria | Southwest
PPP2 | 563980 | 564000 | 20 | CIS of Eger Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4321 | -78.586 | 40.4321 | -78.586 | Cresson Township | Cambria | Southwest
PPP2 | 566564 | 566939 | 375 | GAS of Eger Rd | Weather Permitting | 3 days | Cannot properly backfill due to snow in the ditch | 40.4269 | -78.5818 | 40.426 | -78.5813 | Cresson Township | Cambria | Southwest
PPP2 | 567787 | 567932 | 145 | GAS of Eger Rd | Weather Permitting | 2 days | Cannot properly backfill due to snow in the ditch | 40.4243 | -78.5792 | 40.424 | -78.5789 | Cresson Township | Cambria | Southwest
The winter weather had the most significant impact on Spread 2, in Westmoreland, Indiana, and Cambria counties.

## Southcentral
Requests to Backfill Trenches - More Than 10 Days Needed- Southcentral
Spread | Station Start | Station End | Footage | Description | Projected Start Date | Projected Date of Backfill Completion | Reason/Justification | LAT Start | LONG Start | LAT End | LONG End | Municipality | County | DEP Region
PPP3 | 667400 | 667850 | 450 | Locke Mountain Rd | TBD when weather allows | TBD when weather allows | Due to steep, Icy terrain - unsafe | 40.4311 | -78.2862 | 40.4306 | -78.2847 | FRANKSTOWN | Blair | Southcentral
PPP3 | 668300 | 668320 | 20 | Locke Mountain Rd | TBD when weather allows | TBD when weather allows | Due to steep, Icy terrain - unsafe | 40.4302 | -78.2833 | 40.4302 | -78.2832 | WOODBURY | Blair | Southcentral
PPP3 | 672300 | 672380 | 80 | Locke Mountain Rd | TBD when weather allows | TBD when weather allows | Due to steep, Icy terrain - unsafe | 40.4345 | -78.2732 | 40.4344 | -78.2729 | WOODBURY | Blair | Southcentral
PPP3 | 690936 | 691111 | 175 | Clover Creek | TBD when weather allows | TBD when weather allows | Due to steep, Icy terrain - unsafe Test Site | 40.4203 | -78.209 | 40.4201 | -78.2084 | WOODBURY | Blair | Southcentral
PPP3 | 691111 | 691286 | 175 | Clover Creek | TBD when weather allows | TBD when weather allows | Due to steep, Icy terrain - unsafe Test Site | 40.4201 | -78.2084 | 40.42 | -78.2078 | WOODBURY | Blair | Southcentral
PPP3 | 707367 | 707542 | 175 | Redstone Ridge | TBD when weather allows | TBD when weather allows | Due to steep, Icy terrain - unsafe Test Site | 40.3989 | -78.1595 | 40.3985 | -78.1594 | Penn | Huntingdon | Southcentral
PPP3 | 707542 | 707717 | 175 | Redstone Ridge | TBD when weather allows | TBD when weather allows | Due to steep, Icy terrain - unsafe Test Site | 40.3985 | -78.1594 | 40.3982 | -78.1589 | Penn | Huntingdon | Southcentral
PPP3 | 785170 | 785400 | 230 | Test Site Suchan Lane | TBD | 2 days | Test Site | 40.3372 | -77.9127 | 40.3374 | -77.9119 | Shirley | Huntingdon | Southcentral
PPP3 | 803440 | 803760 | 400 | Coming Inside Cummings Rd. | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.3419 | -77.8503 | 40.3418 | -77.8492 | Shirley | Huntingdon | Southcentral
PPP3 | 804300 | 804860 | 560 | Going Away Side Cummings Rd. | TBD when weather allows | 3 days | Due to steep, Icy terrain - unsafe | 40.3412 | -77.8475 | 40.3405 | -77.8457 | Shirley | Huntingdon | Southcentral
PPP3 | 805000 | 805120 | 120 | Going Away Side Cummings Rd. | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.3403 | -77.8452 | 40.3402 | -77.8449 | Shirley | Huntingdon | Southcentral
PPP3 | 819641 | 819671 | 30 | Coming in side Blacklog Mountain Rd. | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.3232 | -77.7991 | 40.3232 | -77.7989 | Shirley | Huntingdon | Southcentral
PPP3 | 820662 | 820752 | 90 | Going away side of Blacklog Mtn. Rd. | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.3225 | -77.7955 | 40.3225 | -77.7952 | Shirley | Huntingdon | Southcentral
PPP3 | 821435 | 821475 | 40 | Coming in side of Blacklog Valley Rd. | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.3221 | -77.7928 | 40.3221 | -77.7926 | Shirley | Huntingdon | Southcentral
PPP3 | 821502 | 821702 | 200 | Coming in side of Blacklog Valley Rd. | TBD when weather allows | 2 days | Due to steep, Icy terrain - unsafe | 40.3221 | -77.7925 | 40.322 | -77.7918 | Shirley | Huntingdon | Southcentral
PPP3 | 827037 | 827115 | 100 | Shade Mountain | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.3181 | -77.7734 | 40.318 | -77.7731 | Shirley | Huntingdon | Southcentral
PPP3 | 827694 | 828218 | 524 | Shade Mountain | TBD when weather allows | 3 days | Due to steep, Icy terrain - unsafe | 40.3176 | -77.7711 | 40.3168 | -77.7697 | Shirley | Huntingdon | Southcentral
PPP3 | 863400 | 863506 | 106 | Coming in side of Concord Rd. | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.2926 | -77.6485 | 40.2925 | -77.6482 | Toboyne | Perry | Southcentral
PPP3 | 866867 | 866968 | 101 | Going Away Side Concord Rd. | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.2902 | -77.6365 | 40.2901 | -77.6362 | Toboyne | Perry | Southcentral
PPP3 | 867340 | 867410 | 70 | Coming Inside Inner Connect | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.2898 | -77.6349 | 40.2898 | -77.6346 | Toboyne | Perry | Southcentral
PPP3 | 868040 | 868100 | 60 | Going away side of Inner Connect | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.2893 | -77.6325 | 40.2892 | -77.6323 | Toboyne | Perry | Southcentral
PPP3 | 900675 | 901000 | 325 | Between Wolf Narrows 1 to Wolf Narrows 2 | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.2698 | -77.5193 | 40.2696 | -77.5182 | Jackson | Perry | Southcentral
PPP3 | 901200 | 901742 | 542 | Between Wolf Narrows 1 to Wolf Narrows 2 | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.2692 | -77.5176 | 40.2687 | -77.5158 | Jackson | Perry | Southcentral
PPP3 | 902200 | 902790 | 590 | Between Wolf Narrows 2 to Bower Mtn. Rd | TBD when weather allows | 1 day | Due to steep, Icy terrain - unsafe | 40.2684 | -77.5142 | 40.2679 | -77.5122 | Jackson | Perry | Southcentral
PPP3 | 904300 | 905600 | 1300 | Between Bower Mtn. Rd. to Chimney Rocks Rd. | TBD when weather allows | 4 days | Due to steep, Icy terrain - unsafe | 40.2665 | -77.5071 | 40.2654 | -77.5031 | Jackson | Perry | Southcentral
PPP4 | 9095+00 | 910200 | 700 | test break between Spread 3 & 4 | TBD when weather allows | 5 days | access to this locaction is steep/icy terrain - unsafe - Tuscarora State Forest requested it be left open due to road conditions in the forest. | 40.2622 | -77.4903 | 40.2615 | -77.4876 | Jackson | Perry | Southcentral

## Southeast
Requests to Backfill Trenches - More Than 10 Days Needed- Southeast
Spread | Station Start | Station End | Footage | Description | Projected Start Date | Projected Date of Backfill Completion | Reason/Justification | LAT Start | LONG Start | LAT End | LONG End | Municipality | County | DEP Region
PPP6 | 1474086 | 1474432 | 346 | Turnpike #2 20" Bore. Start and complete bore. Leave entry and exit pits open to allow future tie-ins. | Upon release from PADEP |  | Leave pits open with engineered trench boxes to allow future tie-ins. Backfilling and reexcavating increases risk of pipe damage since depth prevents the use of a spotter. Depth is estimated at 20'. | 40.0923 | -75.7332 | 40.0927 | -75.7326 | UPPER UWCHLAN | Chester | Southeast
PPP6 | 1477300 | 1477661 | 361 | Turnpike #3. 16" & 20" Bore. Leave entry and exit pits open to allow future tie-ins. | Upon release from PADEP |  | Leave pits open with engineered trench boxes to allow future tie-ins. Backfilling and reexcavating increases risk of pipe damage since depth prevents the use of a spotter. Depth is estimated at 20'. | 40.0874 | -75.7242 | 40.0868 | -75.7233 | UPPER UWCHLAN | Chester | Southeast