## Table 14-1 JPA Printout
County | Municipality | Date Initial Letter Sent | Initial Delivery Confirmation | Follow-up Letter Sent | Follow-up Delivery Confirmation | Response Received | Stormwater Plan Consistent | Floodplain Consistent
Chester | East Goshen | 2015-11-18 | 2015-11-19 | N/A | N/A | 2015-12-07 | TBD | Y
| East Nantmeal | 2015-11-18 | 2015-11-19 | N/A | N/A | 2015-12-07 | TBD | TBD
| East Whiteland | 2015-12-03 | 2015-12-04 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Elverson | 2015-11-18 | 2015-11-19 | N/A | N/A | 2015-11-25 | N | Y
| Upper Uwchlan | 2015-11-18 | 2015-11-23 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Uwchlan | 2015-11-18 | 2015-11-19 | N/A | N/A | 2015-12-10 | TBD | Y
| Wallace | 2015-11-18 | 2015-11-19 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| West Goshen | 2015-11-18 | 2015-11-19 | N/A | N/A | 3/1/16 - More information requested | TBD | TBD
| West Nantmeal | 2015-11-18 | 2015-11-23 | N/A | N/A | 2015-12-17 | Y | Y
| Westtown | 2015-11-18 | 2015-11-19 | N/A | N/A | 2015-12-07 | Y | Y
| West Whiteland | 2015-11-18 | 2015-11-19 | 2016-02-08 | 2016-02-09 | 2/17/2016 More information requested | TBD | TBD
Delaware | Aston | 2015-11-18 | 2015-11-19 | 2016-02-08 | 2016-02-09 | 2016-02-25 | Y | Y
| Brookhaven | 2015-11-18 | 2015-11-19 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Chester | 2015-11-18 | 2015-11-19 | 2016-02-08 | 2016-02-09 | Pending | TBD | TBD
| Edgmont | 2015-11-18 | 2015-11-19 | N/A | N/A | 2016-01-19 | TBD - Requires Grading Permit for Stormwater Management Consistency Review | Y
| Middletown | 2015-11-18 | 2015-11-19 | 2016-02-08 | 2016-02-09 | 2016-02-12 | N | Y
| Thornbury | 2015-11-18 | 2015-11-19 | 2016-02-08 | 2016-02-09 | 2016-02-17 | TBD | Y
| Upper Chichester | 2015-11-18 | 2015-11-19 | N/A | N/A | None Required - No Act 167 Plan | N/A | N/A
Formulas:
Date Initial Letter Sent = '[1]Tracking Sheet'!H3
Initial Delivery Confirmation = '[1]Tracking Sheet'!I3
Response Received = '[1]Tracking Sheet'!J3
Follow-up Letter Sent = '[1]Tracking Sheet'!M5